## Comments
COMMISSIONING SKELETON SCIENCE ACTIVITY PLAN REQUIREMENT FORM
Data Item | Entry
Document Name | Ralph Commissioning Design Plan
Document Number | 05310.05-COM-RQMTS-01 (original version)
Document Held At
Submission Date | 2004-10-27
Revision Number | 2004-10-27
Submitted By | Henry Throop
Brief Synopsis and Notes:
Ralph Commissioning Phases - Ralph-001: Instrument Functionality Test - Ralph-002: Instrument Power Up/Down Macro Test - Ralph-003: IEM Test - Ralph-004: Door Opening - Ralph-005: Optical Calibration: Stellar Source - Ralph-006: Optical Calibration: Jovian Source - Ralph-007: OpNav: KBO Test - Ralph-008: Multiple Instrument Operations - Ralph-009: Stray Light Test - Ralph-010: Solar Illumination Aperture (SIA) Test - Ralph-011: OpNav: End-to-End Test - Ralph-012: EEPROM Maintenence
Summary of Changes:
Draft 3 (J. Hanley) | Comments from telecon with Ann Harch, Debi Rose and Dennis Reuter (11/06/2003 15:30 CST) incorporated. Main changes: - For all Phases: better estimate on high-speed telemetry based on Dennis Reuter calculations. - Use of LEISA Raw (unsubtracted) deleted
Draft 4 (H. Throop) | Many changes based on commissioning narrative and subsequence discussions with DCR, SAS, LAY, AH. - Added observations to Science Performance Verification - Many small changes and fixes - Added detail to all phases - Revised telemetry estimates - Swapped order of Ralph-005 and Ralph-006
Draft 5 (H. Throop) 20-Mar-2004 | Minor changes
Draft 6 (H. Throop) 20-May-2004 | Changes in response to upcoming Commissioning Design Review - Added test of NOP command - Added test of Ralph hardline reset circuit - Added LEISA geometric calibration - Added LEISA raw mode - Added SIA tests - Added IEM tests - Added OpNav test - Re-numbered many segments - Many small changes
Draft 7 (H. Throop) 9-Jun-2004 | - Lowered maximum TDI rates to 84 Hz (from 120 / 195 Hz) to reflect new instrument capabilities - Changed angles for solar stray light to reflect new MVIC modeling - Added LEISA_RAW observations - Added additional scan to SIA acceptance test
27-Oct-2004 (H. Throop) | - Made major changes to all phases, reflecting ongoing work of Ralph Commissioning Working Group and feedback from Commissioning Design Review. - Integrated all phases and all commanding spreadsheets into one file.
Notes:
Decontamination heaters are always to be turned off 10 hrs before observations, and turned on immediately following observations.
Downlink data volumes are raw and assume no compression.
Setup and overhead times for slews and exposure are TBD; therefore, all slew and imaging times are TBR.
Many commands will be uploaded as CAS/FRAG commands. For clarity, all instrument-level commands are explicitly listed in these spreadsheets; they have not been condensed into CAS/FRAG commands.
For brevity, Ralph TDI and LEISA commands do not explicitly list RATE_MIN, RATE_MAX, RATE_BACKUP, LEISA_OFFSET, and CB3 flag arguments, because these will be constants for most observations. The exposure times listed here as arguments will be taken from the Observation Table for the sequence
Low-speed telemetry from Ralph Status (ApID 500, 65 bytes, 1 Hz) is to be monitored continually throughout all phases.
Hihg-speed telemetry sizes: MVIC pan frame: 5000 x 128 x 12 = 8 Mbits per 128-row image MVIC Color TDI: 5000 x 32 x 4 x 12 = 8 Mbits per 4-color 32-row image = 0.24 Mbits per 4-color row Pan1,2 TDI: 5000 x 32 x 12 = 2 Mbits per 32-row image = 0.06 Mbits per row Pan bin: 5000 x 32 x 12 x 2 / (3x3) = 4 Mbits per 11-row pair image = 0.04 Mbits per row pair LEISA: 256 x 256 x 12 = 0.8 Mbits per 256x256 frame

## 001 Inst Func
COMMISSIONING SKELETON SCIENCE ACTIVITY PLAN REQUIREMENT FORM |  | High-Speed Data Volume
Data Item | Entry | Mode | Mbits/frame | Frames | Fraction | Tot Mbits
Date Updated |  | Framing | 8 | 12 | 1 | 96
Commissioning Requirement Number | Ralph-001 | Pan 1 | 0.06 | 600 | 1 | 36
Commissioning Requirement Name | Instrument Functionality Test | Pan 2 | 0.06 | 600 | 1 | 36
Objective | Perform initial instrument turn-on and functional checkout with aperture door closed. | Pan Bin | 0.04 | 600 | 1 | 24
Estimated Max Power (Watts) | 6.11 W while running MVIC Color mode | MVIC Color | 0.24 | 600 | 1 | 144
Estimate Total Data (Mbits) | 432 | LEISA CDS | 0.8 | 40 | 1 | 32
Estimated Time to Complete | 1 hour All images to be downlinked during current pass. Second day requested as backup | LEISA RAW | 1.6 | 40 | 1 | 64
Real Time Contact Requirement | Yes - RTLT ~ 5 min. Although we will not wait for round-trip confirmation of each command, we request real-time contact as a safety measure. In general Ralph does not have `dangerous' commands; e.g., there is no HVPS that can be affected by improper commanding. | Total |  |  |  | 432
Pointing Requirement | +Y to Earth; 3-axis stabilized. Preference is for a TBD star field with some bright targets given pointing restriction. Pointing is a preference but not requirement, and S/C may not be able to accommodate.
Other Instrument Required | None
Special S/C Requirements | None Door is closed; therefore no pointing restriction from Sun. Decontamination heaters are to be turned off 10 hours (TBR) before sequence.
STOL (R/T) SEQ or Stored Command SEQ | R/T STOL, for two reasons. First, we must wait ground confirmation to proceed after monitoring HK data following turnon, which requires STOL. Second, Ops during this period disallows SEQ because of the likelyhood of sequences being moved in time.
Timing Constraints | > TBD days after launch. Phase will occur during the 'Initial Activation Period' for all instruments, which is a 2-week block starting 3-4 weeks after launch.
Precursor Commissioning Requirements | None
Brief Synopsis and Notes:
This is the first time we power on the instrument. We will put it through a series of checks to verify functionality on both sides, and then acquire data in all modes. Because we are Earth-pointed and the door is closed (reducing throughput to 20%), the data will be used only to perform first-order analysis to identify any gross detector anomalies. LEISA RAW data may be used for dark-current calibration and monitoring. Sequences assumes IEM side A, and checks out Ralph sides A and B. - Power on Ralph side A and enter CHECKOUT mode - Monitor R/T telemetry for anomalies (10 minutes, 1/sec) - Load bytes into EEPROM and RAM and verify proper writing - Perform RALPH_GO and NOP commands - Calculate checksums of all EEPROM images - Operate all relays - Perform hard-line reset from S/C - Acquire data in all MVIC, LEISA modes. - Repeat entire test on Ralph side B Data volume can be reduced by taking fewer MVIC and LEISA frames at each step. We monitor the Ralph Status ApID 500 continually; data volume at 65 bps is negligible (< 2 Mbit)

## 001
Ralph-001 Commanding -- Instrument Functionality Test E. Weigle / H. Throop
| Action | Comment | Time(s) | Total Time (s)
1 | RALPH_DEC_HTR_POWER OFF | Turn off Ralph decontamination heaters 10 hours before start of sequence | 1
2 | RALPH_LVPS_POWER A_CDBOTH ON | Spacecraft powers Ralph. | 14 | 14 | Blue - Comments
3 | RALPH_RELAY_POWER A_CDBOTH ON | Turn on Ralph relay bus | 2 | 16 | Yellow - Spacecraft level command, not Ralph firmware command.
4 | CMD RALPH_SIDESEL_RLY | Pull relays to correct DE side, and wait | 2 | 18 | Green - Pause here until we decide it is okay to proceed. This implies waiting before executing the current line.
5 | RALPH_RELAY_POWER A_CDBOTH OFF |  | 2 | 20 | Purple - Commands dealing with binary EEPROM images.
6 | CMD RALPH_STATE CHECKOUT | Put Ralph in Checkout State,we will wait here for 10 minutes just to collect some HK data for our initial turn-on. | 600 | 620 | NOTE - STOL WAIT Times are included in the Step time; the WAIT command is not shown
7 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "pattern.bin" | Send the command to upload a file to the SCRATCH area. Real STOL has a feature to upload an entire file, however, this may be a macro feature. I am not sure but I am trying to find out. Right now I am assuming we will load a pattern into the unused region of the EEPROM (0x1f800 - 0x1ffff), so this time estimate based on writing to that entire area. "pattern.bin" is TBD. | 20 | 640
8 | CMD RALPH_LOAD_MEMORY 0x1f800 EXPERT PATCH EEPBLK2 "pattern.bin" | patch the pattern to EEPROM memory. It is put in a portion that is not used for Code images, nor Tables. | 5 | 645
9 | CMD RALPH_NOP | Send the NOP command | 1 | 646
10 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "newcode.bin" | Upload some executable code to SCRATCH. Assume we can do it in less than 1K. What the code should do is TBD. | 10 | 656
11 | CMD RALPH_LOAD_MEMORY 0xAB00 EXPERT PATCH RAM1 "newcode.bin" | Patch the code to RAM. | 5 | 661
12 | CMD RALPH_GO 0xFFFD | Arm the GO Command to jump to the next address received. | 1 | 662
13 | CMD RALPH_GO 0xAB00 | Jump to 0xAB00, and execute the code we just uploaded. Pause here until we see the desired response on telemetry(~ 5 minutes), then proceed. | 300 | 962
The following commands will let us know if any of the code images stored in EEPROM are invalid
14 | CMD RALPH_LOAD_MEMORY 0 0x9ffc NORMAL CHKSUM EEPCODE1 | Have the firmware calculate the checksum for EEPCODE1, and send the result | 15 | 977
15 | CMD RALPH_LOAD_MEMORY 0 0x9ffc NORMAL CHKSUM EEPCODE2 | Have the firmware calculate the checksum for EEPCODE2, and send the result | 15 | 992
16 | CMD RALPH_LOAD_MEMORY 0 0x9ffc NORMAL CHKSUM EEPCODE3 | Have the firmware calculate the checksum for EEPCODE3, and send the result | 15 | 1007
14 | CMD RALPH_DUMP_MEMORY 0 300 NORMAL DUMP EEPCODE2 | Dump the first 300 bytes of the second code image in EEPROM. We can continue sending commands, because the memory dump works in the background. | 1 | 1008
15 | RALPH_RELAY_POWER A_CDBOTH ON | Turn on the relay bus for relay testing | 2 | 1010
16 | CMD RALPH GROUP_RELAY 1 | Command group relay 1 -on; group 2 - off; group 3-off. The command only takes a second to execute, but WAIT here 60 seconds, so we have time to see the relay status and read voltages in telemetry. | 60 | 1070
17 | CMD RALPH GROUP_RELAY 2 | Command group relay 1 -off; group 2 - on; group 3-off. The command only takes a second to execute, but WAIT here 60 seconds, so we have time to see the relay status and read voltages in telemetry. | 60 | 1130
18 | CMD RALPH GROUP_RELAY 4 | Command group relay 1 -off; group 2 - off; group 3-on. The command only takes a second to execute, but WAIT here 60 seconds, so we have time to see the relay status and read voltages in telemetry. | 60 | 1190
19 | CMD RALPH GROUP_RELAY ALL_OFF | Turn all the relays OFF | 2 | 1192
20 | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off the relay bus | 2 | 1194
21 | RALPH_HW_RST_RESET A_CDA | Hardline reset from Spacecraft. When Ralphfw boots up, it should be in ACQUIRE mode, so we can continue with putting into acquire modes. | 14 | 1208
22 | RALPH_RELAY_POWER A_CDBOTH ON | Turn on Ralph relay bus | 2 | 1210
23 | CMD RALPH_GROUP_RLY PAN_FRAME | Turn on the relays for PAN_FRAME mode | 2 | 1212
24 | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off Ralph relay bus, and wait 1 second | 2 | 1214
25 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 1224
26 | CMD RALPH_MVIC_PAN_FRAME 500 | Put into acquire mode, and acquire 3 frames. | 8 | 1232
27 | CMD RALPH_IDLE | Idle between observations | 1 | 1233
28 | CMD RALPH_MVIC_PAN_FRAME 1500 | Put into acquire mode, and acquire 3 pan frames | 12 | 1245
29 | CMD RALPH_IDLE | Idle between observations | 1 | 1246
30 | RALPH_RELAY_POWER A_CDBOTH ON | Turn on Ralph relay bus | 2 | 1248
31 | CMD RALPH_GROUP_RLY MVIC_TDI_PAN1 | Turn on the relays for PAN1 mode | 1 | 1249
32 | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off Ralph relay bus | 2 | 1251
33 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 1261
34 | CMD RALPH_MVIC_PAN1_FRCD 6666 | Put into PAN 1 acquire mode @ 15Hz, and acquire 100 frames. | 10 | 1271
35 | CMD RALPH_IDLE | Idle between observations | 1 | 1272
36 | CMD RALPH_MVIC_PAN1_FRCD 1613 | Put into PAN 1 acquire mode @ 62Hz, and acquire 100 frames. | 10 | 1282
37 | CMD RALPH_IDLE | Idle between observations | 1 | 1283
38 | CMD RALPH_MVIC_PAN1_FRCD 1190 | Put into PAN 1 acquire mode @ 84Hz, and acquire 100 frames. | 10 | 1293
39 | CMD RALPH_IDLE | Idle between observations | 1 | 1294
40 | RALPH_RELAY_POWER A_CDBOTH ON | Turn on Ralph relay bus | 2 | 1296
41 | CMD RALPH_GROUP_RLY MVIC_TDI_PAN2 | Set up relays for PAN 2 | 1 | 1297
42 | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off Ralph relay bus | 2 | 1299
43 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 1309
44 | CMD RALPH_MVIC_PAN2_FRCD 6666 | Put into PAN 2 acquire mode @ 15Hz, and acquire 100 frames. | 10 | 1319
45 | CMD RALPH_IDLE | Idle between observations | 1 | 1320
46 | CMD RALPH_MVIC_PAN2_FRCD 1613 | Put into PAN 2 acquire mode @ 62Hz, and acquire 100 frames. | 10 | 1330
47 | CMD RALPH_IDLE | Idle between observations | 1 | 1331
48 | CMD RALPH_MVIC_PAN2_FRCD 1190 | Put into PAN 2 acquire mode @ 84Hz, and acquire 100 frames. | 10 | 1341
49 | CMD RALPH_IDLE | Idle between observations | 1 | 1342
50 | RALPH_RELAY_POWER A_CDBOTH ON | Turn on Ralph relay bus | 2 | 1344
51 | CMD RALPH_GROUP_RLY MVIC_TDI_COLOR__MVIC_TDI_PANBIN | Set up relays for PAN BIN | 1 | 1345
52 | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off Ralph relay bus | 2 | 1347
53 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 1357
54 | CMD RALPH_MVIC_PBIN_FRCD 6666 | Put into PAN BIN acquire mode @TBD Hz, and acquire 100 frames. | 10 | 1367
55 | CMD RALPH_IDLE | Idle between observations | 1 | 1368
56 | CMD RALPH_MVIC_PBIN_FRCD 1613 | Put into PAN BIN acquire mode @ TBD Hz, and acquire 100 frames. | 10 | 1378
57 | CMD RALPH_IDLE | Idle between observations | 1 | 1379
58 | CMD RALPH_MVIC_PBIN_FRCD 1190 | Put into PAN BIN acquire mode @ TBD Hz, and acquire 100 frames. | 8 | 1387
59 | CMD RALPH_IDLE | Idle between observations | 1 | 1388
60 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 1398
61 | CMD RALPH_MVIC_COLR_FRCD 13333 | Put into COLOR acquire mode @ 7.5Hz, and acquire 100 frames. | 20 | 1418
62 | CMD RALPH_IDLE | Idle between observations | 1 | 1419
63 | CMD RALPH_MVIC_COLR_FRCD 3333 | Put into COLOR acquire mode @ 30Hz, and acquire 100 frames. | 10 | 1429
64 | CMD RALPH_IDLE | Idle between observations | 1 | 1430
65 | CMD RALPH_MVIC_COLR_FRCD 2000 | Put into COLOR acquire mode @ 50Hz, and acquire 100 frames. | 12 | 1442
66 | CMD RALPH_IDLE | Idle between observations | 1 | 1443
67 | RALPH_RELAY_POWER A_CDBOTH ON | Turn on Ralph relay bus | 2 | 1445
68 | CMD RALPH_GROUP_RLY ALL_OFF | Turn off all the relays | 1 | 1446
69 | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off Ralph relay bus | 2 | 1448
70 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 1458
70 | CMD RALPH_LEISA_FRCD 1000 | Put into LEISA acquire mode @ 1Hz, and acquire 10 frames. | 20 | 1478
71 | CMD RALPH_IDLE | Idle between observations | 1 | 1479
72 | CMD RALPH_LEISA_FRCD 200 | Put into LEISA acquire mode @ 5Hz, and acquire 10 frames. | 10 | 1489
73 | CMD RALPH_IDLE | Idle between observations | 1 | 1490
74 | CMD RALPH_LEISA_RAW_FRCD 1000 | Put into LEISA_RAW acquire mode @ 1Hz, and acquire 10 frames. | 20 | 1510
75 | CMD RALPH_IDLE | Idle between observations | 1 | 1511
76 | CMD RALPH_LEISA_RAW_FRCD 200 | Put into LEISA RAW acquire mode @ 5Hz, and acquire 10 frames. | 10 | 1521
77 | CMD RALPH_IDLE | Idle between observations | 1 | 1522
78 | RALPH_LVPS_POWER A_CDBOTH OFF | Turn PRIME side of RALPH Off | 2 | 1524
Begin on Ralph side B
79 | RALPH_LVPS_POWER B_CDBOTH ON | Spacecraft powers Ralph. | 14 | 1538
80 | RALPH_RELAY_POWER B_CDBOTH ON | Turn on Ralph relay bus | 2 | 1540
81 | CMD RALPH_SIDESEL_RLY | Pull relays to correct DE side, and wait | 1 | 1541
82 | RALPH_RELAY_POWER B_CDBOTH OFF |  | 2 | 1543
83 | CMD RALPH_STATE CHECKOUT | Put Ralph in Checkout State,we will wait here for 10 minutes just to collect some HK data for our initial turn-on. | 600 | 2143
84 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "pattern.bin" | Send the command to upload a file to the SCRATCH area. Real STOL has a feature to upload an entire file, however, this may be a macro feature. I am not sure but I am trying to find out. Right now I am assuming we will load a pattern into the unused region of the EEPROM (0x1f800 - 0x1ffff), so this time estimate based on writing to that entire area. "pattern.bin" is TBD. | 20 | 2163
85 | CMD RALPH_LOAD_MEMORY 0x1f800 EXPERT PATCH EEPBLK2 "pattern.bin" | patch the pattern to EEPROM memory. It is put in a portion that is not used for Code images, nor Tables. | 5 | 2168
86 | CMD RALPH_NOP | Send the NOP command | 1 | 2169
87 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "newcode.bin" | Upload some executable code to SCRATCH. Assume we can do it in less than 1K. What the code should do is TBD. | 10 | 2179
88 | CMD RALPH_LOAD_MEMORY 0xAB00 EXPERT PATCH RAM1 "newcode.bin" | Patch the code to RAM. | 5 | 2184
89 | CMD RALPH_GO 0xFFFD | Arm the GO Command to jump to the next address received. | 1 | 2185
90 | CMD RALPH_GO 0xAB00 | Jump to 0xAB00, and execute the code we just uploaded. Pause here until we see the desired response on telemetry(~ 5 minutes) , then proceed. | 300 | 2485
The following commands will let us know if any of the code images stored in EEPROM are invalid
91 | CMD RALPH_LOAD_MEMORY 0 0x9ffc NORMAL CHKSUM EEPCODE1 | Have the firmware calculate the checksum for EEPCODE1, and send the result | 15 | 2500
92 | CMD RALPH_LOAD_MEMORY 0 0x9ffc NORMAL CHKSUM EEPCODE2 | Have the firmware calculate the checksum for EEPCODE2, and send the result | 15 | 2515
93 | CMD RALPH_LOAD_MEMORY 0 0x9ffc NORMAL CHKSUM EEPCODE3 | Have the firmware calculate the checksum for EEPCODE3, and send the result | 15 | 2530
91 | CMD RALPH_DUMP_MEMORY 0 300 NORMAL DUMP EEPCODE2 | Dump the first 300 bytes of the second code image in EEPROM. We can continue sending commands, because the memory dump works in the background. | 1 | 2531
92 | RALPH_RELAY_POWER B_CDBOTH ON | Turn on the relay bus for relay testing | 2 | 2533
93 | CMD RALPH GROUP_RELAY 1 | Command group relay 1 -on; group 2 - off; group 3-off. The command only takes a second to execute, but WAIT here 60 seconds, so we have time to see the relay status and read voltages in telemetry. | 60 | 2593
94 | CMD RALPH GROUP_RELAY 2 | Command group relay 1 -off; group 2 - on; group 3-off. The command only takes a second to execute, but WAIT here 60 seconds, so we have time to see the relay status and read voltages in telemetry. | 60 | 2653
95 | CMD RALPH GROUP_RELAY 4 | Command group relay 1 -off; group 2 - off; group 3-on. The command only takes a second to execute, but WAIT here 60 seconds, so we have time to see the relay status and read voltages in telemetry. | 60 | 2713
96 | CMD RALPH GROUP_RELAY ALL_OFF | Turn all the relays OFF | 60 | 2773
97 | RALPH_RELAY_POWER B_CDBOTH OFF | Turn off the relay bus | 2 | 2775
98 | RALPH_HW_RST_RESET B_CDA | Hardline reset from Spacecraft. When Ralphfw boots up, it should be in ACQUIRE mode, so we can continue with putting into acquire modes. | 14 | 2789
99 | RALPH_RELAY_POWER B_CDBOTH ON | Turn on Ralph relay bus | 2 | 2791
100 | CMD RALPH_GROUP_RLY PAN_FRAME | Turn on the relays for PAN_FRAME mode | 2 | 2793
101 | RALPH_RELAY_POWER B_CDBOTH OFF | Turn off Ralph relay bus | 2 | 2795
102 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 2805
103 | CMD RALPH_MVIC_PAN_FRAME 500 | Put into acquire mode, and acquire 3 frames. | 8 | 2813
104 | CMD RALPH_IDLE | Idle between observations | 1 | 2814
105 | CMD RALPH_MVIC_PAN_FRAME 1500 | Put into acquire mode, and acquire 3 frames. | 11 | 2825
106 | CMD RALPH_IDLE | Idle between observations | 1 | 2826
107 | RALPH_RELAY_POWER B_CDBOTH ON | Turn on Ralph relay bus | 2 | 2828
108 | CMD RALPH_GROUP_RLY MVIC_TDI_PAN1 | Turn on the relays for PAN1 mode | 1 | 2829
109 | RALPH_RELAY_POWER B_CDBOTH OFF | Turn off Ralph relay bus | 2 | 2831
110 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 2841
111 | CMD RALPH_MVIC_PAN1_FRCD 6666 | Put into PAN 1 acquire mode @ 15Hz, and acquire 100 frames. | 10 | 2851
112 | CMD RALPH_IDLE | Idle between observations | 1 | 2852
113 | CMD RALPH_MVIC_PAN1_FRCD 1613 | Put into PAN 1 acquire mode @ 62Hz, and acquire 100 frames. | 10 | 2862
114 | CMD RALPH_IDLE | Idle between observations | 1 | 2863
115 | CMD RALPH_MVIC_PAN1_FRCD 1190 | Put into PAN 1 acquire mode @ 84Hz, and acquire 100 frames. | 10 | 2873
116 | CMD RALPH_IDLE | Idle between observations | 1 | 2874
117 | RALPH_RELAY_POWER B_CDBOTH ON | Turn on Ralph relay bus | 2 | 2876
118 | CMD RALPH_GROUP_RLY MVIC_TDI_PAN2 | Set up relays for PAN 2 | 1 | 2877
119 | RALPH_RELAY_POWER B_CDBOTH OFF | Turn off Ralph relay bus | 2 | 2879
120 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 2889
121 | CMD RALPH_MVIC_PAN2_FRCD 6666 | Put into PAN 2 acquire mode @ 15Hz, and acquire 100 frames. | 10 | 2899
122 | CMD RALPH_IDLE | Idle between observations | 1 | 2900
123 | CMD RALPH_MVIC_PAN2_FRCD 1613 | Put into PAN 2 acquire mode @ 62Hz, and acquire 100 frames. | 10 | 2910
124 | CMD RALPH_IDLE | Idle between observations | 1 | 2911
125 | CMD RALPH_MVIC_PAN2_FRCD 1190 | Put into PAN 2 acquire mode @ 84Hz, and acquire 100 frames. | 10 | 2921
126 | CMD RALPH_IDLE | Idle between observations | 1 | 2922
127 | RALPH_RELAY_POWER B_CDBOTH ON | Turn on Ralph relay bus | 2 | 2924
128 | CMD RALPH_GROUP_RLY MVIC_TDI_COLOR__MVIC_TDI_PANBIN | Set up relays for PAN BIN | 1 | 2925
129 | RALPH_RELAY_POWER B_CDBOTH OFF | Turn off Ralph relay bus | 2 | 2927
130 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 2937
131 | CMD RALPH_MVIC_PBIN_FRCD 6666 | Put into PAN BIN acquire mode @ TBD Hz, and acquire 100 frames | 10 | 2947
132 | CMD RALPH_IDLE | Idle between observations | 1 | 2948
133 | CMD RALPH_MVIC_PBIN_FRCD 1613 | Put into PAN BIN acquire mode @ TBD Hz, and acquire 100 frames. | 10 | 2958
134 | CMD RALPH_IDLE | Idle between observations | 1 | 2959
135 | CMD RALPH_MVIC_PBIN_FRCD 1190 | Put into PAN BIN acquire mode @ TBD Hz, and acquire 100 frames. | 10 | 2969
136 | CMD RALPH_IDLE | Idle between observations | 1 | 2970
137 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 2980
138 | CMD RALPH_MVIC_COLR_FRCD 13333 | Put into COLOR acquire mode @ 7.5Hz, and acquire 100 frames. | 20 | 3000
139 | CMD RALPH_IDLE | Idle between observations | 1 | 3001
140 | CMD RALPH_MVIC_COLR_FRCD 3333 | Put into COLOR acquire mode @ 30Hz, and acquire 100 frames. | 10 | 3011
141 | CMD RALPH_IDLE | Idle between observations | 1 | 3012
142 | CMD RALPH_MVIC_COLR_FRCD 2000 | Put into COLOR acquire mode @ 50Hz, and acquire 100 frames. | 10 | 3022
143 | CMD RALPH_IDLE | Idle between observations | 1 | 3023
144 | RALPH_RELAY_POWER B_CDBOTH ON | Turn on Ralph relay bus | 2 | 3025
145 | CMD RALPH_GROUP_RLY ALL_OFF | Turn off all the relays | 1 | 3026
146 | RALPH_RELAY_POWER B_CDBOTH OFF | Turn off Ralph relay bus | 2 | 3028
147 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 3038
147 | CMD RALPH_LEISA_FRCD 1000 | Put into LEISA acquire mode @ 1Hz, and acquire 10 frames. | 20 | 3058
148 | CMD RALPH_IDLE | Idle between observations | 1 | 3059
149 | CMD RALPH_LEISA_FRCD 200 | Put into LEISA acquire mode @ 5Hz, and acquire 10 frames. | 10 | 3069
150 | CMD RALPH_IDLE | Idle between observations | 1 | 3070
151 | CMD RALPH_LEISA_RAW_FRCD 1000 | Put into LEISA_RAW acquire mode @ 1Hz, and acquire 10 frames. | 20 | 3090
152 | CMD RALPH_IDLE | Idle between observations | 1 | 3091
153 | CMD RALPH_LEISA_RAW_FRCD 200 | Put into LEISA RAW acquire mode @ 5Hz, and acquire 10 frames. | 10 | 3101
154 | CMD RALPH_IDLE | Idle between observations | 1 | 3102
155 | RALPH_LVPS_POWER B_CDBOTH OFF | Turn PRIME side of RALPH Off | 2 | 3104
| RALPH_DEC_HTR_POWER ON | Turn on decontamination heaters | 1

## 002 Power
COMMISSIONING SKELETON SCIENCE ACTIVITY PLAN REQUIREMENT FORM |  | High-Speed Data Volume
Data Item | Entry | Mode | Mbits/frame | Frames | Fraction | Tot Mbits
Date Updated |  | Framing | 8 | 0 | 1 | 0
Commissioning Requirement Number | Ralph-002 | Pan 1 | 0.06 | 0 | 1 | 0
Commissioning Requirement Name | Sequenced Power Up/Down Test | Pan 2 | 0.06 | 0 | 1 | 0
Objective | We use sequenced commands to turn Ralph on and off on sides A and B. No data acquisition. | Pan Bin | 0.04 | 0 | 1 | 0
Estimated Max Power (Watts) |  | MVIC Color | 0.24 | 0 | 1 | 0
Estimated Total Data (Mbits) | 0 | LEISA CDS | 0.8 | 0 | 1 | 0
Estimated Time to Complete | 1 hour | LEISA RAW | 1.6 | 0 | 1 | 0
Real Time Contact Requirement | None | Total |  |  |  | 0
Pointing Requirement | None
Other Instrument Required | None
Special S/C Requirements | None
STOL (R/T) SEQ or Stored Command SEQ | SEQ. (TBR: can we really pause for ground confirmation during SEQ?)
Timing Constraints | > TBD days after launch
Precursor Commissioning Requirements | Ralph-001
Brief Synopsis and Notes:
We use sequenced commands to turn Ralph on and off on sides A and B. No data acquisition. This is the first time we operate in SEQ mode. Ralph-001 performed these commands but using STOL, not SEQ. We monitor the Ralph Status ApID 500 continually; data volume at 65 bps is negligible (< 2 Mbit)

## 002
Ralph-002 Commanding - Sequenced Power Up/Down Test E. Weigle / H. Throop
Step | Action | Comment | Time(s) | Total Time (s)
1 | RALPH_DEC_HTR_POWER OFF | Turn off Ralph decontamination heaters 10 hours before start of sequence | 1
Power on Ralph side A
1 | RALPH_LVPS_POWER A_CDBOTH ON | Spacecraft powers Ralph. | 11 | 11 | Blue - Comments
2 | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph, and wait 1 second | 2 | 13 | Yellow - Spacecraft level command, not Ralph firmware command.
3 | CMD RALPH_SIDESEL_RLY | Pull relays to correct DE side, and wait | 1 | 14 | Green - Pause here until we decide it is okay to proceed. This implies waiting before executing the current line
4 | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off the relay bus | 1 | 15
5 | Pause until valid telemetry is seen (TBR: we are SEQ and therefore Pause is not possible) |  | 300 | 315
6 | Power off Ralph side A
7 | RALPH_LVPS_POWER A_CDBOTH OFF | Spacecraft powers off Ralph. | 2 | 317
Repeat sequence on Ralph side B
| Power on Ralph side B |  |  | 317
8 | RALPH_LVPS_POWER B_CDBOTH ON | Spacecraft powers Ralph. | 11 | 328
9 | RALPH_RELAY_POWER B_CDBOTH ON | Energize the relay bus for Ralph, and wait 1 second | 2 | 330
10 | CMD RALPH_SIDESEL_RLY | Pull relays to correct DE side, and wait | 1 | 331
11 | RALPH_RELAY_POWER B_CDBOTH OFF | Turn off the relay bus | 1 | 332
12 | Pause until valid telemetry is seen (TBR: we are SEQ and therefore Pause is not possible) |  | 300 | 632
13 | Power off Ralph side B |  |  | 632
14 | RALPH_LVPS_POWER B_CDBOTH OFF | Spacecraft powers off Ralph. | 1 | 633
15 | RALPH_DEC_HTR_POWER ON | Turn on decontamination heaters | 1 | 634

## 003 IEM
COMMISSIONING SKELETON SCIENCE ACTIVITY PLAN REQUIREMENT FORM |  | High-Speed Data Volume
Data Item | Entry | Mode | Mbits/frame | Frames | Fraction | Tot Mbits
Date Updated |  | Framing | 8 | 8 | 1 | 64
Commissioning Requirement Number | Ralph-003 | Pan 1 | 0.06 | 200 | 1 | 12
Commissioning Requirement Name | IEM Test | Pan 2 | 0.06 | 200 | 1 | 12
Objective | Verify proper instrument operation with side B of S/C IEM. Test is based on Ralph-001, which uses side A of IEM | Pan Bin | 0.04 | 200 | 1 | 8
Estimated Max Power (Watts) | 6.11 W while running MVIC Color mode | MVIC Color | 0.24 | 200 | 1 | 48
Estimated Total Data (Mbits) | 163.2 | LEISA CDS | 0.8 | 8 | 1 | 6.4
Estimated Time to Complete | 1 hour All images to be downlinked during current pass. Second day requested as backup | LEISA RAW | 1.6 | 8 | 1 | 12.8
Real Time Contact Requirement | None | Total |  |  |  | 163.2
Pointing Requirement | +Y to Earth; 3-axis stabilized. Preference is for a TBD star field used in Ralph-001, but this is not a requirement.
Other Instrument Required | None
Special S/C Requirements | None Door is closed so no pointing restriction from Sun. Decontamination heaters turned off 10 hours (TBR) before sequence.
STOL (R/T) SEQ or Stored Command SEQ | TBD, depending on S/C power and Ops constraints
Timing Constraints | Executed during S/C IEM checkout.
Precursor Commissioning Requirements | Ralph-001
Brief Synopsis and Notes:
This phase is an abridged repeat of Ralph-001, running through IEM B. We operate both Ralph sides A and B.. The purpose is not to repeat a full functional test, but to verify the instrument's basic ability to be commanded and return data through IEM B. Ops would like to keep this to a maximum of 30-40 minutes. High-speed data cannot be downlinked immediately due to Ops constraints and limited software support as of Aug-2004. Data will be downlinked at a TBD time after observation. This software limitation is expected to be removed at some point after launch. We monitor the Ralph Status ApID 500 continually; data volume at 65 bps is negligible (< 2 Mbit)

## 003
Ralph-003 Commanding -- IEM Test E. Weigle / H. Throop
Step | Action | Comment | Time(s) | Total Time (s)
1 | RALPH_DEC_HTR_POWER OFF | Turn off Ralph decontamination heaters 10 hours before start of sequence | 1
Begin on Ralph side A
1 | RALPH_LVPS_POWER A_CDBOTH ON | Spacecraft powers Ralph. | 14 | 14
2 | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph (SC command), and wait 1 second | 2 | 16 | Blue - Comments
3 | CMD RALPH_SIDESEL_RLY | Pull relays to correct DE side, and wait | 1 | 17 | Yellow - Spacecraft level command, not Ralph firmware command.
4 | RALPH_RELAY_POWER A_CDBOTH OFF |  | 2 | 19 | Green - Pause here until we decide it is okay to proceed. This implies waiting before executing the current line
5 | CMD RALPH_STATE CHECKOUT | Put Ralph in Checkout State and collect some HK data. | 60 | 79 | Purple - TBD dealing with binary EEPROM image
6 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "pattern2.bin" | Send the command to upload a file to the SCRATCH area. Real STOL has a feature to upload an entire file, however, this may be a macro feature. I am not sure but I am trying to find out. Right now I am assuming we will load a pattern into the unused region of the EEPROM (0x1f800 - 0x1ffff), so this time estimate based on writing to that entire area. "pattern2.bin" is TBD, however, it is different than "pattern.bin" which was used in Ralph-001.. | 20 | 99
7 | CMD RALPH_LOAD_MEMORY 0x1f800 EXPERT PATCH EEPBLK2 "pattern2.bin" | patch the pattern to EEPROM memory. It is put in a portion that is not used for Code images, nor Tables. | 5 | 104
8 | CMD RALPH_NOP | Send the NOP command | 1 | 105
9 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "newcode.bin" | Upload some executable code to SCRATCH. Assume we can do it in less than 1K. What the code should do is TBD. | 10 | 115
10 | CMD RALPH_LOAD_MEMORY 0xAB00 EXPERT PATCH RAM1 "newcode.bin" | Patch the code to RAM. | 5 | 120
11 | CMD RALPH_GO 0xFFFD | Arm the GO Command to jump to the next address received. | 1 | 121
12 | CMD RALPH_GO 0xAB00 | Jump to 0xAB00, and execute the code we just uploaded. | 10 | 131
13 | RALPH_RELAY_POWER A_CDBOTH ON | Turn on the relay bus for relay testing | 2 | 133
14 | CMD RALPH GROUP_RELAY 1 | Command group relay 1 -on; group 2 - off; group 3-off. The command only takes a second to execute, but WAIT here 60 seconds, so we have time to see the relay status and read voltages in telemetry. | 60 | 193
15 | CMD RALPH GROUP_RELAY 2 | Command group relay 1 -off; group 2 - on; group 3-off. The command only takes a second to execute, but WAIT here 60 seconds, so we have time to see the relay status and read voltages in telemetry. | 60 | 253
16 | CMD RALPH GROUP_RELAY 4 | Command group relay 1 -off; group 2 - off; group 3-on. The command only takes a second to execute, but WAIT here 60 seconds, so we have time to see the relay status and read voltages in telemetry. | 60 | 313
17 | CMD RALPH GROUP_RELAY ALL_OFF | Turn all the relays OFF | 2 | 315
18 | Now begin taking data on Ralph side A |  |  | 315
19 | CMD RALPH_GROUP_RLY PAN_FRAME | Turn on the relays for PAN_FRAME mode | 2 | 317
20 | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off Ralph relay bus, and wait 1 second | 2 | 319
21 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 329
22 | CMD RALPH_MVIC_PAN_FRAME 500 | Put into first acquire mode, and acquire 4 pan frames. | 10 | 339
23 | CMD RALPH_IDLE | Idle between modes | 1 | 340
24 | RALPH_RELAY_POWER A_CDBOTH ON | Energize Ralph relay bus, and wait 1 second | 2 | 342
25 | CMD RALPH_GROUP_RLY MVIC_TDI_PAN1 | Turn on the relays for PAN1 mode | 1 | 343
26 | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off Ralph relay bus | 2 | 345
27 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 355
28 | CMD RALPH_MVIC_PAN1_FRCD 1613 | Put into PAN 1 acquire mode @ 62Hz, and acquire 100 frames. | 10 | 365
29 | CMD RALPH_IDLE | Idle between modes | 1 | 366
30 | RALPH_RELAY_POWER A_CDBOTH ON | Energize Ralph relay bus | 2 | 368
31 | CMD RALPH_GROUP_RLY MVIC_TDI_PAN2 | Set up relays for PAN 2 | 1 | 369
32 | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off Ralph relay bus | 2 | 371
33 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 381
34 | CMD RALPH_MVIC_PAN2_FRCD 1613 | Put into PAN 2 acquire mode @ 62Hz, and acquire 100 frames. | 10 | 391
35 | CMD RALPH_IDLE | Idle between modes | 1 | 392
36 | RALPH_RELAY_POWER A_CDBOTH ON | Energize Ralph relay bus | 2 | 394
37 | CMD RALPH_GROUP_RLY MVIC_TDI_COLOR__MVIC_TDI_PANBIN | Set up relays for PAN BIN | 1 | 395
38 | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off Ralph relay bus | 2 | 397
39 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 407
40 | CMD RALPH_MVIC_PBIN_FRCD 1613 | Put into PAN BIN acquire mode @ TBD Hz, and acquire 100 frames. | 10 | 417
41 | CMD RALPH_IDLE | Idle between modes | 1 | 418
42 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 428
43 | CMD RALPH_MVIC_COLR_FRCD 3333 | Put into COLOR acquire mode @ 30Hz, and acquire 100 frames. | 10 | 438
44 | CMD RALPH_IDLE | Idle between modes | 1 | 439
45 | RALPH_RELAY_POWER A_CDBOTH ON | Energize Ralph relay bus | 2 | 441
46 | CMD RALPH_GROUP_RLY ALL_OFF | Turn off all the relays | 1 | 442
47 | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off Ralph relay bus | 2 | 444
48 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 454
49 | CMD RALPH_LEISA_FRCD 1000 | Put into LEISA acquire mode @ 1Hz and acquire 4 frames. | 12 | 466
50 | CMD RALPH_IDLE | Idle between modes | 1 | 467
51 | CMD RALPH_LEISA_RAW_FRCD 1000 | Put into LEISA_RAW acquire mode @ 1Hz and acquire 4 frames. | 12 | 479
52 | CMD RALPH_IDLE | Idle between modes | 1 | 480
53 | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off the relay bus | 2 | 482
54 | RALPH_HW_RST_RESET A_CDA | Hardline reset from Spacecraft | 20 | 502
55 | RALPH_LVPS_POWER A_CDBOTH OFF | Turn PRIME side of RALPH Off | 2 | 504
56 | Repeat above sequence, using Ralph side B |  |  | 504
57 | RALPH_LVPS_POWER B_CDBOTH ON | Spacecraft powers Ralph. | 14 | 518
58 | RALPH_RELAY_POWER B_CDBOTH ON | Energize Ralph relay bus | 2 | 520
59 | CMD RALPH_SIDESEL_RLY | Pull relays to correct DE side, and wait | 1 | 521
60 | RALPH_RELAY_POWER B_CDBOTH OFF |  | 2 | 523
61 | CMD RALPH_STATE CHECKOUT | Put Ralph in Checkout State and collect HK data. | 60 | 583
62 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "pattern.bin" | Send the command to upload a file to the SCRATCH area. Real STOL has a feature to upload an entire file, however, this may be a macro feature. I am not sure but I am trying to find out. Right now I am assuming we will load a pattern into the unused region of the EEPROM (0x1f800 - 0x1ffff), so this time estimate based on writing to that entire area. "pattern.bin" is TBD. | 20 | 603
63 | CMD RALPH_LOAD_MEMORY 0x1f800 EXPERT PATCH EEPBLK2 "pattern.bin" | patch the pattern to EEPROM memory. It is put in a portion that is not used for Code images, nor Tables. | 5 | 608
64 | CMD RALPH_NOP | Send the NOP command | 1 | 609
65 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "newcode.bin" | Upload some executable code to SCRATCH. Assume we can do it in less than 1K. What the code should do is TBD. | 10 | 619
66 | CMD RALPH_LOAD_MEMORY 0xAB00 EXPERT PATCH RAM1 "newcode.bin" | Patch the code to RAM. | 5 | 624
67 | CMD RALPH_GO 0xFFFD | Arm the GO Command to jump to the next address received. | 1 | 625
68 | CMD RALPH_GO 0xAB00 | Jump to 0xAB00, and execute the code we just uploaded. | 10 | 635
69 | RALPH_RELAY_POWER B_CDBOTH ON | Turn on the relay bus for relay testing | 2 | 637
70 | CMD RALPH GROUP_RELAY 1 | Command group relay 1 -on; group 2 - off; group 3-off. The command only takes a second to execute, but WAIT here 60 seconds, so we have time to see the relay status and read voltages in telemetry. | 60 | 697
71 | CMD RALPH GROUP_RELAY 2 | Command group relay 1 -off; group 2 - on; group 3-off. The command only takes a second to execute, but WAIT here 60 seconds, so we have time to see the relay status and read voltages in telemetry. | 60 | 757
72 | CMD RALPH GROUP_RELAY 4 | Command group relay 1 -off; group 2 - off; group 3-on. The command only takes a second to execute, but WAIT here 60 seconds, so we have time to see the relay status and read voltages in telemetry. | 60 | 817
73 | CMD RALPH GROUP_RELAY ALL_OFF | Turn all the relays OFF | 60 | 877
74 | Now begin taking data on Ralph side B |  |  | 877
75 | CMD RALPH_GROUP_RLY PAN_FRAME | Turn on the relays for PAN_FRAME mode | 2 | 879
76 | RALPH_RELAY_POWER B_CDBOTH OFF | Turn off Ralph relay bus | 2 | 881
77 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 891
78 | CMD RALPH_MVIC_PAN_FRAME 500 | Put into first acquire mode, and acquire 4 pan frames. | 10 | 901
79 | CMD RALPH_IDLE | Idle between modes | 1 | 902
80 | RALPH_RELAY_POWER B_CDBOTH ON | Energize Ralph relay bus, and wait 1 second | 2 | 904
81 | CMD RALPH_GROUP_RLY MVIC_TDI_PAN1 | Turn on the relays for PAN1 mode, and wait 1 second | 1 | 905
82 | RALPH_RELAY_POWER B_CDBOTH OFF | Turn off Ralph relay bus, and wait 1 second | 2 | 907
83 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 917
84 | CMD RALPH_MVIC_PAN1_FRCD 1613 | Put into PAN 1 acquire mode @ 62Hz, and acquire 100 frames. | 10 | 927
85 | CMD RALPH_IDLE | Idle between modes | 1 | 928
86 | RALPH_RELAY_POWER B_CDBOTH ON | Energize Ralph relay bus, and wait 1 second | 2 | 930
87 | CMD RALPH_GROUP_RLY MVIC_TDI_PAN2 | Set up relays for PAN 2 | 1 | 931
88 | RALPH_RELAY_POWER B_CDBOTH OFF | Turn off Ralph relay bus | 2 | 933
89 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 943
90 | CMD RALPH_MVIC_PAN2_FRCD 1613 | Put into PAN 2 acquire mode @ 62Hz, and acquire 100 frames. | 10 | 953
91 | CMD RALPH_IDLE | Idle between modes | 1 | 954
92 | RALPH_RELAY_POWER B_CDBOTH ON | Energize Ralph relay bus | 2 | 956
93 | CMD RALPH_GROUP_RLY MVIC_TDI_COLOR__MVIC_TDI_PANBIN | Set up relays for PAN BIN | 1 | 957
94 | RALPH_RELAY_POWER B_CDBOTH OFF | Turn off Ralph relay bus | 2 | 959
95 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 969
96 | CMD RALPH_MVIC_PBIN_FRCD 1613 | Put into PAN BIN acquire mode @ TBD Hz, and acquire 100 frames. | 10 | 979
97 | CMD RALPH_IDLE | Idle between modes | 1 | 980
98 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 990
99 | CMD RALPH_MVIC_COLR_FRCD 3333 | Put into COLOR acquire mode @ 30Hz, and acquire 100 frames. | 10 | 1000
100 | CMD RALPH_IDLE | Idle between modes | 1 | 1001
101 | RALPH_RELAY_POWER B_CDBOTH ON | Energize Ralph relay bus | 2 | 1003
102 | CMD RALPH_GROUP_RLY ALL_OFF | Turn off all the relays | 1 | 1004
103 | RALPH_RELAY_POWER B_CDBOTH OFF | Turn off Ralph relay bus | 2 | 1006
104 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 1016
105 | CMD RALPH_LEISA_FRCD 1000 | Put into LEISA acquire mode @ 1Hz and acquire 4 frames. | 12 | 1028
106 | CMD RALPH_IDLE | Idle between modes | 1 | 1029
107 | CMD RALPH_LEISA_RAW_FRCD 1000 | Put into LEISA_RAW acquire mode @ 1Hz and acquire 4 frames. | 12 | 1041
108 | CMD RALPH_IDLE | Idle between modes | 1 | 1042
109 | CMD RALPH GROUP_RELAY ALL_OFF | Turn all the relays OFF | 60 | 1102
110 | RALPH_RELAY_POWER B_CDBOTH OFF | Turn off the relay bus | 2 | 1104
111 | RALPH_HW_RST_RESET B_CDA | Hardline reset from Spacecraft. | 60 | 1164
112 | RALPH_LVPS_POWER B_CDBOTH OFF | Turn REDUNDANT side of RALPH Off | 2 | 1166
113 | RALPH_DEC_HTR_POWER ON | Turn on decontamination heaters | 1 | 1167

## 004 Door Opening
COMMISSIONING SKELETON SCIENCE ACTIVITY PLAN REQUIREMENT FORM |  | High-Speed Data Volume
Data Item | Entry | Mode | Mbits/frame | Frames | Fraction | Tot Mbits
Date Updated |  | Framing | 8 | 8 | 1 | 64
Commissioning Requirement Number | Ralph-004 | Pan 1 | 0.06 | 0 | 1 | 0
Commissioning Requirement Name | Door Opening | Pan 2 | 0.06 | 0 | 1 | 0
Objective | - Open the Ralph door and verify that it has been fully opened | Pan Bin | 0.04 | 0 | 1 | 0
Estimated Max Power (Watts) | 6.11 W while running MVIC Color Mode 1.5 W for 250 msec when pin puller is activated | MVIC Color | 0.24 | 0 | 1 | 0
Estimated Total Data (Mbits) | 64 | LEISA CDS | 0.8 | 0 | 1 | 0
Estimated Time to Complete | 1 hour | LEISA RAW | 1.6 | 0 | 1 | 0
Real Time Contact Requirement | Yes | Total |  |  |  | 64
Pointing Requirement | Starfield TBD, with restriction +Y toward Earth. Door must be opened while 3-axis stabilized. Ralph must be pointed at same starfield before and after opening to verify proper opening.
Other Instrument Required | No
Special S/C Requirements | S/C commanding of door opening mechanism
STOL (R/T) SEQ or Stored Command SEQ | Stored Command SEQ. STOL would provide no advantage because sequence does not depend on input from the ground.
Timing Constraints | >2.4 AU
Precursor Commissioning Requirements | Ralph-001
Brief Synopsis and Notes:
We activate Ralph's one-time aperture door. When the door is closed, throughput is reduced to 20%. The door covers the joint aperture for MVIC and LEISA. - Turn on Ralph - Observe a starfield with framing camera at several exposure lengths - Turn off Ralph (for safety; not a technical requirement) - Open aperture door - Turn on Ralph - Observe same starfield to verify door opening - Turn off Ralph We monitor the Ralph Status ApID 500 continually; data volume at 65 bps is negligible (< 2 Mbit). We also monitor raw gyro and accelerometer data at 100 Hz for approx 10 seconds surrounding the pin-puller activation. These data will be used as diagnostic to detect recoil motion of the door as necessary. APIDs 0x131, 0x132, 0x133, 0x134 (gyro) APIDs 0x135, 0x136, 0x137, 0x138 (accelerometer)

## 004
Ralph-004 Commanding -- Door Opening E. Weigle / H. Throop
Step | Action | Comment | Time(s) | Total Time (s)
1 | RALPH_DEC_HTR_POWER OFF | Turn off Ralph decontamination heaters 10 hours before start of sequence | 1
2 | POSITION RALPH TO STARFIELD |  | 3600 | 3600
3 | TIGHTEN DEADBAND TO SMALLEST NOMINAL RATE AND POSITION. | Keep starfield in FOV throughout sequence. | 30 | 3630
4 | RALPH_LVPS_POWER A_CDBOTH ON | Spacecraft powers Ralph. | 14 | 3614
5 | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph and wait 1 second | 2 | 3616 | Blue - Comments
6 | CMD RALPH_SIDESEL_RLY | Pull relays to correct DE side, and wait | 1 | 3617 | Orange - G&C Command
7 | CMD RALPH_GROUP_RLY PAN_FRAME | Turn on the relays for PAN_FRAME mode | 2 | 3619 | Yellow - Spacecraft command
8 | RALPH_RELAY_POWER A_CDBOTH OFF |  | 2 | 3621 | White - Ralph command
9 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 3631
10 | CMD RALPH_MVIC_PAN_FRAME 250 | Put into acquire mode. | 1 | 3632
11 | CMD RALPH_IDLE | Put in IDLE mode. | 1 | 3633
12 | CMD RALPH_MVIC_PAN_FRAME 1500 | Put into acquire mode. | 2 | 3635
13 | CMD RALPH_IDLE | Put in IDLE mode, and wait a second. | 1 | 3636
14 | CMD RALPH_GROUP_RLY 0 | Turn off all the relays, and wait 1 second |  | 3636
15 | RALPH_LVPS_POWER A_CDBOTH OFF | Turn PRIME side of RALPH Off | 2 | 3638
16 | NOW ACTIVATE THE PIN-PULLER, CAUSING DOOR TO OPEN |  | 5 | 3643
17 | S/C ACTIVATES PIN PULLER | Open the door, and wait TBD seconds |  | 3643
18 | RALPH_LVPS_POWER A_CDBOTH ON | Spacecraft powers Ralph. | 14 | 3657
19 | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph and wait 1 second | 2 | 3659
20 | CMD RALPH_SIDESEL_RLY | Pull relays to correct DE side, and wait | 1 | 3660
21 | CMD RALPH_GROUP_RLY PAN_FRAME | Turn on the relays for PAN_FRAME mode | 2 | 3662
22 | RALPH_RELAY_POWER A_CDBOTH OFF |  | 2 | 3664
23 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 3674
24 | CMD RALPH_MVIC_PAN_FRAME 250 | Put into acquire mode. | 1 | 3675
25 | CMD RALPH_IDLE | Put in IDLE mode. | 1 | 3676
26 | CMD RALPH_MVIC_PAN_FRAME 1500 | Put into acquire mode. | 2 | 3678
27 | CMD RALPH_IDLE | Put in IDLE mode. | 1 | 3679
28 | CMD RALPH_GROUP_RLY 0 | Turn off all the relays, and wait 1 second |  | 3679
29 | RALPH_LVPS_POWER A_CDBOTH OFF | Turn PRIME side of RALPH Off | 2 | 3681
30 | RALPH_DEC_HTR_POWER ON | Turn on decontamination heaters | 1 | 3682

## 005 Geom Cal
COMMISSIONING SKELETON SCIENCE ACTIVITY PLAN REQUIREMENT FORM |  | High-Speed Data Volume
Data Item | Entry | Mode | Mbits/frame | Frames | Fraction | Tot Mbits
Date Updated |  | Framing | 8 | 36 | 1 | 288
Commissioning Requirement Number | Ralph-005 | Pan 1 | 0.06 | 200 | 1 | 12
Commissioning Requirement Name | Optical Calibration: Stellar Source | Pan 2 | 0.06 | 200 | 1 | 12
Objective | Perform scans across fixed starfield at a variety of rates & modes to verify instrument optical performance and s/c pointing performance for both MVIC and LEISA. These are our first calibration observations with the door open. Data will be used for radiometric and geometric calibration and to assess TDI performance. | Pan Bin | 0.04 | 200 | 1 | 8
Estimated Max Power (Watts) | 6.11 W (MVIC Color Mode) | MVIC Color | 0.24 | 4500 | 1 | 1080
Estimated Total Data (Mbits) | 2040 | LEISA CDS | 0.8 | 400 | 1 | 320
Estimated Time to Complete | 1 hour | LEISA RAW | 1.6 | 200 | 1 | 320
Real Time Contact Requirement | No | Total |  |  |  | 2040
Pointing Requirement | Standard Ralph calibration starfield M6-M8 (TBR). This is a 1deg x 5 deg cluster. MVIC is rotated at 90 deg to mine between M6 and M8, so that we can scan a full 5 deg w/o having to repoint. We will observe cluster stars in the center of the FOV and field stars at the edges.
Other Instrument Required | None
Special S/C Requirements | None
STOL (R/T) SEQ or Stored Command SEQ | Stored Command SEQ
Timing Constraints | None
Precursor Commissioning Requirements | Ralph-004
Brief Synopsis and Notes:
We perform a number of observations of a standard calibration starfield. We will use the results to perform geometric and radiometric calibration, because we know the intrinsic spectrum and position of each of the stars. We will also use scans at different rates to verify proper operation of the TDI as it obtains rate information from G&C. The calibration field is the M6-M8 region (TBR), which has a variety of stellar types and brightnesses, and is approx. 5x2 deg across. The s/c will be rotated such that the star field crosses the MVIC FOV at approx 45 deg, allowing us to observe stars on both LHS and RHS of focal plane in one scan. We will reset the scan position as necessary to stay in the field, but in order to minimize fuel usage, we do not repoint after each scan. All of the short scans (100 lines) overlap with the large, 5x5 deg color scan, for context and comparison information. 100 lines should be sufficient to get several stars in the field, but this is TBR. The 1.5 Hz and 6.5 Hz LEISA rates are based on 1 Hz and 7 Hz min and max clock rates, with 34 urad/sec G&C uncertainty. MVIC rates are based on similar constraints. Data can be windowed for downlink as necessary. Nominal downlink is 1.7 hours per 100 Mbits.
Thrusters are inhibited during all MVIC observations because this is the nominal operating mode. Maximum drift based on 34 urad/sec rate uncertainty is is approx 100 pixels cross-track at end of 5 deg scan at 54 Hz. Because the starrfield is dense, it is not necessary to remain within a deadband for pointing precision. A deadband may be set if it is desired to assess G&C performance on this scan. The nominal order of operation for performing a scan is: Point to starting location Tighten deadbands in rate and/or position Initiate scan Change thrusters to either 'inhibited' (MVIC TDI) or 'cross-track stabilized' (LEISA). Scans may vary from this for various purposes.
The following scans will be performed - MVIC Color TDI, 54 Hz, 4300 lines (for a 5 deg x 5 deg scan to simulate that at Pluto C/A) - Repoint to starting location - MVIC Color TDI, 10 Hz, 100 lines - MVIC Color TDI, 50 Hz, 100 lines - MVIC Pan Bin, 5 Hz, 100 lines - MVIC Pan Bin, 28 Hz, 100 lines - MVIC Pan 1, 16 Hz, 100 lines - MVIC Pan 1, 84 Hz, 100 lines - MVIC Pan 2, 16 Hz, 100 lines - MVIC Pan 2, 82 Hz, 100 lines - Repoint as needed to center M6 or M8 on LEISA - LEISA 1.5 Hz, forward, 100 frames - LEISA 1.5 Hz, reverse, 100 frames - LEISA 6.5 Hz, forward, 100 frames - LEISA 6.5 Hz, reverse, 100 frames - LEISA RAW, 6.5 Hz, forward, 100 frames - LEISA RAW, 6.5 Hz, reverse, 100 frames - MVIC Framing, Field A, 3 each of 0.25, 1, 4, 10 sec (3 overlapping fields) - MVIC Framing, Field B, 3 each of 0.25, 1, 4, 10 sec - MVIC Framing, Field C, 3 each of 0.25, 1, 4, 10 sec We monitor the Ralph Status ApID 500 continually; data volume at 65 bps is negligible (< 2 Mbit)

## 005
Ralph-005 Commanding -- Optical Calibration: Stellar Source H. Throop
Step |  | Action | Comment | Time(s) | Total Time (s)
1 |  | RALPH_DEC_HTR_POWER OFF | Turn off Ralph decontamination heaters 10 hours before start of sequence | 1
2 |  | POINT S/C TO STARTING LOCATION AT EDGE OF M6-M8 FIELD, WITH MVIC FOV ROTATED APPROX 45 DEG FROM LINE CONNECTING M6 AND M8. |  | 3600 | 3600 | Orange - G&C command
3 |  | TIGHTEN DEADBAND TO SMALLEST NOMINAL RATE AND POSITION |  | 30 | 3630
4 |  | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph, and wait 1 second | 2 | 3632 | Yellow - Spacecraft command
5 |  | CMD RALPH_SIDESEL_RLY | Pull relays to correct DE side, and wait | 1 | 3633 | White - Ralph command
6 |  | CMD RALPH_GROUP_RLY MVIC_TDI_COLOR__MVIC_TDI_PANBIN | Turn on the relays for PAN COLOR mode, and wait 1 second | 1 | 3634
7 |  | RALPH_RELAY_POWERA_CDBOTH_OFF | Turn off the relay bus, and wait 1 second | 2 | 3636 | All slew times are taken as 150 sec min (TBR). All rate changes are taken as 30 sec (TBR).
8 | Color 54 Hz 5deg x 5deg scan | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 3646
9 |  | INITIATE SCAN: 1080 URAD/SEC; INHIBIT THRUSTERS | 1080 urad/sec = 54 Hz |  | 3646
10 |  | CMD_RALPH_MVIC_COLOR | Acquire 5 deg scan (4400 frames) using calculated TMR rate | 70 | 3716
11 |  | CMD_RALPH_IDLE |  | 1 | 3717
12 |  | REPOINT S/C TO STARTING LOCATION, BEING CERTAIN POSITION IS CONTAINED WITHIN 5x5 DEG SCAN GIVEN POINTING UNCERTAINTY. |  | 150 | 3867
13 |  | TIGHTEN DEADBAND TO SMALLEST NOMINAL RATE AND POSITION |  | 30 | 3897
14 | Color 10 Hz | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 3907
15 |  |  |  |  | 3907
16 |  | CMD_RALPH_MVIC_COLOR | Acquire 100 frames using calculated TMR rate | 10 | 3917
17 |  | CMD_RALPH_IDLE |  | 1 | 3918
18 | Color 50 Hz | INITIATE SCAN: 1000 URAD/SEC; INHIBIT THRUSTERS | 1000 urad/sec = 50 Hz | 30 | 3948
19 |  | CMD_RALPH_MVIC_COLOR | Acquire 100 frames using calculated TMR rate | 20 | 3968
20 |  | CMD_RALPH_IDLE |  |  | 3968
21 |  |  |  |  | 3968
22 | Pan Bin 5.33 Hz | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 3978
23 |  | INITIATE SCAN: 320 URAD/SEC; INHIBIT THRUSTERS | 320 urad/sec = 5.33 Hz | 30 | 4008
24 |  | CMD_RALPH_MVIC_PAN_BIN | Acquire 100 frames using calculated TMR rate | 25 | 4033
25 |  | CMD_RALPH_IDLE |  | 1 | 4034
26 | Pan Bin 28 Hz | INITIATE SCAN: 1680 URAD/SEC; INHIBIT THRUSTERS | 1680 urad/sec = 28 Hz | 30 | 4064
27 |  | CMD_RALPH_MVIC_PAN_BIN | Acquire 100 frames using calculated TMR rate | 5 | 4069
28 |  | CMD_RALPH_IDLE |  | 1 | 4070
29 | Pan1 16 Hz | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph, and wait 1 second | 2 | 4072
30 |  | CMD RALPH_GROUP_RLY MVIC_TDI_PAN1 | Set up relays for PAN 1 | 1 | 4073
31 |  | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off the relay bus, and wait 1 second | 2 | 4075
32 |  | INITIATE SCAN: 320 URAD/SEC; INHIBIT THRUSTERS | 320 urad/sec = 16 Hz | 30 | 4105
33 |  | CMD_RALPH_MVIC_PAN1 | Acquire 100 frames using calculated TMR rate | 2 | 4107
34 | Pan1 84 Hz | INITIATE SCAN: 1680 URAD/SEC; INHIBIT THRUSTERS | 1680 urad/sec = 84 Hz | 30 | 4137
35 |  | CMD_RALPH_MVIC_PAN1 | Acquire 100 frames using calculated TMR rate | 2 | 4139
36 |  | CMD_RALPH_IDLE |  | 1 | 4140
37 | Pan2 16 Hz | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph, and wait 1 second | 2 | 4142
38 |  | CMD RALPH_GROUP_RLY MVIC_TDI_PAN2 | Set up relays for PAN 2 | 1 | 4143
39 |  | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off the relay bus, and wait 1 second | 2 | 4145
40 |  | INITIATE SCAN: 320 URAD/SEC; INHIBIT THRUSTERS | 1680 urad/sec = 16 Hz | 30 | 4175
41 |  | CMD_RALPH_MVIC_PAN2 | Acquire 100 frames using calculated TMR rate | 2 | 4177
42 |  | CMD_RALPH_IDLE |  | 1 | 4178
43 | Pan2 84 Hz | INITIATE SCAN: 1680 URAD/SEC; INHIBIT THRUSTERS | 1680 urad/sec = 84 Hz | 30 | 4208
44 |  | CMD_RALPH_MVIC_PAN2 | Acquire 100 frames using calculated TMR rate | 2 | 4210
45 |  | CMD_RALPH_IDLE |  | 1 | 4211
46 |  | REPOINT S/C SO THAT LEISA FOV IS CENTERED ON M6 OR M8 (TBD) |  | 150 | 4361
47 |  | TIGHTEN DEADBAND TO SMALLEST NOMINAL RATE AND POSITION |  | 30 | 4391
48 | LEISA 1 Hz | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph, and wait 1 second | 2 | 4393
49 |  | CMD RALPH_GROUP_RLY ALL_OFF | Turn off relays for LEISA | 1 | 4394
50 |  | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off the relay bus, and wait 1 second | 2 | 4396
51 |  | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 4406
52 |  | INITIATE SCAN: 61.54 URAD/SEC; INHIBIT THRUSTERS | 61.54 urad/sec = 1 Hz | 30 | 4436
53 |  | CMD_RALPH_LEISA | Acquire 100 frames using calculated TMR rate | 100 | 4536
54 |  | CMD_RALPH_IDLE |  | 1 | 4537
55 |  | INITIATE SCAN: -61.54 URAD/SEC; INHIBIT THRUSTERS | 61.54 urad/sec = 1 Hz | 30 | 4567
56 |  | CMD_RALPH_LEISA REVERSE | Acquire 100 frames using calculated TMR rate | 100 | 4667
57 |  | CMD_RALPH_IDLE |  | 1 | 4668
58 | LEISA 7 Hz | INITIATE SCAN: 430.78 URAD/SEC; INHIBIT THRUSTERS | 430.78 urad/sec = 7 Hz | 30 | 4698
59 |  | CMD_RALPH_LEISA | Acquire 100 frames using calculated TMR rate | 15 | 4713
60 |  | CMD_RALPH_IDLE |  | 1 | 4714
61 |  | INITIATE SCAN: -430.78 URAD/SEC; INHIBIT THRUSTERS | 430.78 urad/sec = 7 Hz | 30 | 4744
62 |  | CMD_RALPH_LEISA REVERSE | Acquire 100 frames using calculated TMR rate | 15 | 4759
63 |  | CMD_RALPH_IDLE |  | 1 | 4760
64 | LEISA 7 Hz RAW | INITIATE SCAN: 430.78 URAD/SEC; INHIBIT THRUSTERS | 430.78 urad/sec = 7 Hz | 30 | 4790
65 |  | CMD_RALPH_LEISA_RAW | Acquire 100 frames using calculated TMR rate | 15 | 4805
66 |  | CMD_RALPH_IDLE |  | 1 | 4806
67 |  | INITIATE SCAN: -430.78 URAD/SEC; INHIBIT THRUSTERS | 430.78 urad/sec = 7 Hz | 30 | 4836
68 |  | CMD_RALPH_LEISA_RAW REVERSE | Acquire 100 frames using calculated TMR rate | 15 | 4851
69 |  | CMD_RALPH_IDLE |  | 1 | 4852
70 |  | CMD RALPH_SIDESEL_RLY | Pull relays to correct DE side, and wait | 1 | 4853
71 |  | CMD RALPH_GROUP_RLY PAN_FRAME | Turn on the relays for PAN_FRAME mode | 2 | 4855
72 |  | RALPH_RELAY_POWERA_CDBOTH_OFF | Turn off the relay bus, and wait 1 second | 2 | 4857
73 | MVIC Framing | REPOINT S/C SO THAT MVIC FRAMING FOV IS CENTERED ON M6/M8. | Framing phase includes three overlapping FOV's; starting location same as for TDI scans | 150 | 5007
74 |  | TIGHTEN DEADBAND TO SMALLEST NOMINAL RATE AND POSITION |  | 30 | 5037
75 |  | INHIBIT THRUSTERS DURING MVIC EXPOSURES (TBR) |  |  | 5037
76 |  | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 5047
77 |  | CMD_RALPH_MVIC PAN_FRAME 250 | Acquire 3 0.25 sec frames | 2 | 5049
78 |  | CMD_RALPH_IDLE |  | 1 | 5050
79 |  | CMD_RALPH_MVIC PAN_FRAME 1000 | Acquire 3 1 sec frames | 3 | 5053
80 |  | CMD_RALPH_IDLE |  | 1 | 5054
81 |  | CMD_RALPH_MVIC PAN_FRAME 4000 | Acquire 3 4 sec frames | 12 | 5066
82 |  | CMD_RALPH_IDLE |  | 1 | 5067
83 |  | CMD_RALPH_MVIC PAN_FRAME 10000 | Acquire 3 10 sec frames | 30 | 5097
84 |  | CMD_RALPH_IDLE |  | 1 | 5098
85 |  | POINT S/C TO MOSAIC LOCATION #2 (OVERLAP #1 BY1/2-FOV, SHORT DIR) |  | 150 | 5248
86 |  | TIGHTEN DEADBAND TO SMALLEST NOMINAL RATE AND POSITION |  | 30 | 5278
87 |  | CMD_RALPH_MVIC PAN_FRAME 250 | Acquire 3 0.25 sec frames | 2 | 5280
88 |  | CMD_RALPH_IDLE |  | 1 | 5281
89 |  | CMD_RALPH_MVIC PAN_FRAME 1000 | Acquire 3 1 sec frames | 3 | 5284
90 |  | CMD_RALPH_IDLE |  | 1 | 5285
91 |  | CMD_RALPH_MVIC PAN_FRAME 4000 | Acquire 3 4 sec frames | 12 | 5297
92 |  | CMD_RALPH_IDLE |  | 1 | 5298
93 |  | CMD_RALPH_MVIC PAN_FRAME 10000 | Acquire 3 10 sec frames | 30 | 5328
94 |  | CMD_RALPH_IDLE |  | 1 | 5329
95 |  | POINT S/C TO MOSAIC LOCATION #3 (OVERLAP #2 BY 1/2-FOV, SHORT DIR) |  | 150 | 5479
96 |  | TIGHTEN DEADBAND TO SMALLEST NOMINAL RATE AND POSITION |  | 30 | 5509
97 |  | CMD_RALPH_MVIC PAN_FRAME 250 | Acquire 3 0.25 sec frames | 2 | 5511
98 |  | CMD_RALPH_IDLE |  | 1 | 5512
99 |  | CMD_RALPH_MVIC PAN_FRAME 1000 | Acquire 3 1 sec frames | 3 | 5515
100 |  | CMD_RALPH_IDLE |  | 1 | 5516
101 |  | CMD_RALPH_MVIC PAN_FRAME 4000 | Acquire 3 4 sec frames | 12 | 5528
102 |  | CMD_RALPH_IDLE |  | 1 | 5529
103 |  | CMD_RALPH_MVIC PAN_FRAME 10000 | Acquire 3 10 sec frames | 30 | 5559
104 |  | CMD_RALPH_IDLE |  | 1 | 5560
105 |  | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph, and wait 1 second | 2 | 5562
106 |  | CMD_RALPH_GROUP_RLY ALL_OFF | Turn off all the relays | 1 | 5563
107 |  | RALPH_RELAY_POWERA_CDBOTH_OFF | Turn off the relay bus, and wait 1 second | 2 | 5565
108 |  | RALPH_LVPS_POWERA_CDBOTH OFF | S/C turns off Ralph | 1 | 5566
109 |  | RALPH_DEC_HTR_POWER ON | Turn on decontamination heaters | 1 | 5567

## 006 Jov Cal
COMMISSIONING SKELETON SCIENCE ACTIVITY PLAN REQUIREMENT FORM |  | High-Speed Data Volume
Data Item | Entry | Mode | Mbits/frame | Frames | Fraction | Tot Mbits
Date Updated |  | Framing | 8 | 0 | 1 | 0
Commissioning Requirement Number | Ralph-006 | Pan 1 | 0.06 | 0 | 1 | 0
Commissioning Requirement Name | Optical Calibration: Jovian Source | Pan 2 | 0.06 | 0 | 1 | 0
Objective | Scan MVIC and LEISA across Jupiter to perform radiometric and spectral calibration on an extended target. | Pan Bin | 0.04 | 0 | 1 | 0
Estimated Max Power (Watts) | 6.11 W (MVIC Color Mode) | MVIC Color | 0.24 | 3900 | 0.1 | 93.6
Estimated Total Data (Mbits) | 195.6 | LEISA CDS | 0.8 | 1275 | 0.1 | 102
Estimated Time to Complete | 1 hour | LEISA RAW | 1.6 | 0 | 1 | 0
Real Time Contact Requirement | No | Total |  |  |  | 195.6
Pointing Requirement | Jupiter
Other Instrument Required | None
Special S/C Requirements | None
STOL (R/T) SEQ or Stored Command SEQ | Stored Command SEQ
Timing Constraints | Prefer > 4 AU in order to maximize number of pixels covered by Jovian disk. Can be scheduled earlier as needed by Jupiter science planning and/or to investigate anomalies from stellar calibration.
Precursor Commissioning Requirements | Ralph-004
Brief Synopsis and Notes:
In this step we perform scans across the Jovian disk in order to calibrate MVIC and LEISA. MVIC will be saturated on all but the CH4 channel. LEISA will not be saturated. In both instruments we scan at as high a rate as possible to maximize non-saturated signal. In order to look for spatial variations across the detector, we perform scans across the left, center, and right of the FOV of each detector, for a total of six scans. LEISA scan lengths are determined by summing the following: 0.9 deg = 256 pixels = Detector width 0.05 deg = 15 pixels = Jupiter width at 1.0 AU distance (TBR) 0.05 deg = 12 pixels = Targeting uncertainty Therefore, a 1.0 deg scan = 300 pixels is sufficient to cover all of Jupiter with all LEISA wavelengths. At the highest 7.3 Hz rate, this scan takes 70 seconds. We use cross-track stabilized position deadband because this is our nominal LEISA operating mode. However, this mode is not necessary here because even at the maximum drift rate of 34 urad/sec, Jupiter will stay within the FOV. Thrusters may be inhibited to save propellant. MVIC scan lengths determined in same way as LEISA; approx 1.0 deg (TBR) based on width between color channels. MVIC nominal observation mode is to inhibit thrusters. Both LEISA and MVIC data can be significantly windowed to reduce downlink bandwidth. We monitor the Ralph Status ApID 500 continually; data volume at 65 bps is negligible (< 2 Mbit)

## 006
Commissioning Ralph-006: Optical Calibration: Jovian Source
Step |  | Action | Comment | Time(s) | Total Time (s) | Legend
1 |  | RALPH_DEC_HTR_POWER OFF | Turn off Ralph decontamination heaters 10 hours before start of sequence | 1
2 | LEISA LEFT | POINT S/C TO STARTING LOCATION (JUPITER ALONG LEISA FOV LEFT EDGE) |  | 3600 | 3600
|  | TIGHTEN DEADBAND TO SMALLEST NOMINAL RATE AND POSITION | Deadband will keep Jupiter within LEISA FOV. | 30 | 3630
3 |  | RALPH_LVPS_POWER A_CDBOTH ON | Spacecraft powers Ralph. | 14 | 3614 | Orange - G&C command
4 |  | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 3624 | Yellow - Spacecraft command
5 |  | INITIATE SCAN: 450 URAD/SEC, 1.0 DEG, CROSS-TRACK POSITION STABILIZED | 450 urad/sec = 7.3 Hz |  | 3624 | White - Ralph command
6 |  | CMD_RALPH_LEISA, REVERSE | Acquire data using calculated TMR rate | 70 | 3694 | All slew times are taken as 150 sec min (TBR).
7 |  | CMD_RALPH_IDLE |  | 1 | 3695
8 | LEISA CENTER | POINT S/C TO STARTING LOCATION (LEISA FOV CENTER) |  | 150 | 3845
9 |  | INITIATE SCAN: 450 URAD/SEC, 1.0 DEG, CROSS-TRACK POSITION STABILIZED | 450 urad/sec = 7.3 Hz |  | 3845
10 |  | CMD_RALPH_LEISA, FORWARD | Acquire data using calculated TMR rate | 70 | 3915
11 |  | CMD_RALPH_IDLE |  | 1 | 3916
12 | LEISA RIGHT | POINT S/C TO STARTING LOCATION (LEISA FOV RIGHT EDGE) |  | 150 | 4066
13 |  | INITIATE SCAN: 450 URAD/SEC, 1.0 DEG, CROSS-TRACK POSITION STABILIZED | 450 urad/sec = 7.3 Hz |  | 4066
14 |  | CMD_RALPH_LEISA, REVERSE | Acquire data using calculated TMR rate | 70 | 4136
15 |  | CMD_RALPH_IDLE |  | 1 | 4137
16 |  | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph, and wait 1 second | 2 | 4139
17 |  | CMD RALPH_GROUP_RLY MVIC_TDI_COLOR | Set up relays for TDI COLOR | 1 | 4140
18 |  | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off the relay bus, and wait 1 second | 2 | 4142
19 |  | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 4152
20 | MVIC COLOR LEFT | POINT S/C TO STARTING LOCATION (MVIC COLOR LEFT EDGE) |  | 150 | 4302
21 |  | INITIATE SCAN: 1040 URAD/SEC, 1.0 DEG; INHIBIT THRUSTERS | 1040 urad/sec = 52 Hz |  | 4302
22 |  | CMD_RALPH_MVIC_COLOR | Acquire data using calculated TMR rate | 30 | 4332
23 |  | CMD_RALPH_IDLE |  | 1 | 4333
24 | MVIC COLOR CENTER | POINT S/C TO STARTING LOCATION (MVIC COLOR CENTER EDGE) |  | 150 | 4483
25 |  | INITIATE SCAN: 1040 URAD/SEC, 1.0 DEG; INHIBIT THRUSTERS | 1040 urad/sec = 52 Hz |  | 4483
26 |  | CMD_RALPH_MVIC_COLOR | Acquire data using calculated TMR rate | 30 | 4513
27 |  | CMD_RALPH_IDLE |  | 1 | 4514
28 | MVIC COLOR RIGHT | POINT S/C TO STARTING LOCATION (MVIC COLOR RIGHT EDGE) |  | 150 | 4664
29 |  | INITIATE SCAN: 1040 URAD/SEC, 1.0 DEG; INHIBIT THRUSTERS | 1040 urad/sec = 52 Hz |  | 4664
30 |  | CMD_RALPH_MVIC_COLOR | Acquire data using calculated TMR rate | 30 | 4694
31 |  | CMD_RALPH_IDLE |  | 1 | 4695
32 | POWER OFF | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph, and wait 1 second | 2 | 4697
33 |  | CMD_RALPH_GROUP_RLY ALL_OFF | Turn off all the relays | 1 | 4698
34 |  | RALPH_RELAY_POWERA_CDBOTH_OFF | Turn off the relay bus, and wait 1 second | 2 | 4700
35 |  | RALPH_LVPS_POWERA_CDBOTH OFF | S/C turns off Ralph |  | 4700
36 |  | RALPH_DEC_HTR_POWER ON | Turn on decontamination heaters | 1 | 4701

## 007 OpNav KBO
COMMISSIONING SKELETON SCIENCE ACTIVITY PLAN REQUIREMENT FORM |  | High-Speed Data Volume
Data Item | Entry | Mode | Mbits/frame | Frames | Fraction | Tot Mbits
Date Updated |  | Framing | 8 | 12 | 1 | 96
Commissioning Requirement Number | Ralph-007 | Pan 1 | 0.06 | 0 | 1 | 0
Commissioning Requirement Name | OpNav KBO Test | Pan 2 | 0.06 | 0 | 1 | 0
Objective | Test KBO OpNav capability | Pan Bin | 0.04 | 0 | 1 | 0
Estimated Max Power (Watts) | ? | MVIC Color | 0.24 | 0 | 1 | 0
Estimated Total Data (Mbits) | 96 | LEISA CDS | 0.8 | 0 | 1 | 0
Estimated Time to Complete | 1 hour per 12 image set | LEISA RAW | 1.6 | 0 | 1 | 0
Real Time Contact Requirement | no | Total |  |  |  | 96
Pointing Requirement | targets tbd
Other Instrument Required | No
Special S/C Requirements | None
STOL (R/T) SEQ or Stored Command SEQ | SEQ
Timing Constraints | None
Precursor Commissioning Requirements | Ralph-004
Brief Synopsis and Notes:
Observe either a KBO, an asteroid, or a Jupiter Trojan satellite with the purpose of simulating the OpNav acquisition and analysis processes at the actual KBO Flybys. Each test would consist of four pointings to the object, offset by 1/2 field in the direction normal to the long dimension of the slit. Take 3 exposures at each position for a total of 12 images. Repeat tbd days later. Data volume = 92 Mb for each set of 12 images x 2 executions = 184 Mb per opportunity. Use special KBO OpNav deadband which guarantees a relative drift of no more than 10 microrad over 10 seconds. Exposure times for MVIC framing images are TBD as per consultation with Bobby Williams. Target is TBD and will be selected as per consultation with Yanping Guo. We monitor the Ralph Status ApID 500 continually; data volume at 65 bps is negligible (< 2 Mbit)

## 007
Ralph-007 Commanding: OpNav KBO A. Harch
Step | Action | Comment | Time(s) | Total Time (s)
1 | RALPH_DEC_HTR_POWER OFF | Turn off Ralph decontamination heaters 10 hours before start of sequence | 1
2 | POINT S/C TO STARTING LOCATION. TIGHTEN DEADBAND TO SMALLEST NOMINAL RATE AND POSITION. |  | 3600 | 3600
3 | RALPH_LVPS_POWER A_CDBOTH ON | Spacecraft powers Ralph. | 14 | 3614 | Orange - G&C command
4 | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph (SC command), and wait 1 second | 2 | 3616 | Yellow - Spacecraft command
5 | CMD RALPH_SIDESEL_RLY | Pull relays to correct DE side, and wait | 1 | 3617 | White - Ralph command
6 | CMD RALPH_GROUP_RLY MVIC_PAN_FRAME | Turn on relays for mvic pan frame mode | 1 | 3618 | All slew times are taken as 150 sec min (TBR).
7 | RALPH_RELAY_POWERA_CDBOTH_OFF | Turn off the relay bus (SC command), and wait 1 second | 2 | 3620
8 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enabling the recorder. | 10 | 3610
9 | KBO OPNAV DEADBAND IMPLEMENTATION TBD |  |  | 3610
9 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 1 (short) | 10 | 3620
10 | CMD_RALPH_IDLE |  | 1 | 3621
11 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 2 (med) | 10 | 3631
12 | CMD_RALPH_IDLE |  | 1 | 3632
13 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 3 (long) | 10 | 3642
14 | CMD_RALPH_IDLE |  | 1 | 3643
15 | POINT S/C TO MOSAIC LOCATION #2 (OVERLAP WITH #1 BY 1/2 FOV) |  | 150 | 3793
16 | KBO OPNAV DEADBAND IMPLEMENTATION TBD |  |  | 3793
16 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 1 (short) | 10 | 3803
17 | CMD_RALPH_IDLE |  | 1 | 3804
18 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 2 (med) | 10 | 3814
19 | CMD_RALPH_IDLE |  | 1 | 3815
20 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 3 (long) | 10 | 3825
21 | CMD_RALPH_IDLE |  | 1 | 3826
22 | POINT S/C TO MOSAIC LOCATION #3 (OVERLAP WITH #2 BY 1/2 FOV) |  | 150 | 3976
23 | KBO OPNAV DEADBAND IMPLEMENTATION TBD |  |  | 3976
23 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 1 (short) | 10 | 3986
24 | CMD_RALPH_IDLE |  | 1 | 3987
25 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 2 (med) | 10 | 3997
26 | CMD_RALPH_IDLE |  | 1 | 3998
27 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 3 (long) | 10 | 4008
28 | CMD_RALPH_IDLE |  | 1 | 4009
29 | POINT S/C TO MOSAIC LOCATION #4 (OVERLAP WITH #3 BY 1/2 FOV) |  | 150 | 4159
30 | KBO OPNAV DEADBAND IMPLEMENTATION TBD |  |  | 4159
30 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 1 (short) | 10 | 4169
31 | CMD_RALPH_IDLE |  | 1 | 4170
32 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 2 (med) | 10 | 4180
33 | CMD_RALPH_IDLE |  | 1 | 4181
34 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 3 (long) | 10 | 4191
35 | CMD_RALPH_IDLE |  | 1 | 4192
36 | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph (SC command), and wait 1 second | 2 | 4194
37 | CMD_RALPH_GROUP_RLY ALL_OFF | Turn off all the relays | 1 | 4195
38 | RALPH_RELAY_POWERA_CDBOTH_OFF | Turn off the relay bus (SC command), and wait 1 second | 2 | 4197
39 | RALPH_LVPS_POWERA_CDBOTH OFF | S/C turns off Ralph |  | 4197
40 | RALPH_DEC_HTR_POWER ON | Turn on decontamination heaters | 1 | 4198
Repeat approx one week later (tbd) as Raph-007B

## 008 Multiple Inst Op
COMMISSIONING SKELETON SCIENCE ACTIVITY PLAN REQUIREMENT FORM
Data Item | Entry
Date Updated
Commissioning Requirement Number | Ralph-008
Commissioning Requirement Name | Multiple Instrument Operations / Interference Campaign
Objective | - Check for interference from other instruments to Ralph - Check for interference from Ralph to other instruments
Estimated Max Power (Watts) | 6.11 W (MVIC Color Mode)
Estimate Total Data (Mbits) | TBD
Estimated Time to Complete | TBD
Real Time Contact Requirement | No
Pointing Requirement | Point to Star Pattern and Jupiter
Other Instrument Required | SWAP, PEPPSI, and Alice for interference
Special S/C Requirements | TBD
STOL (R/T) SEQ or Stored Command SEQ | Stored Command SEQ
Timing Constraints | During S/C interference campaign
Precursor Commissioning Requirements | Ralph-004
Brief Synopsis and Notes:
This test is to determine whether Ralph is being affected by other instruments and vice versa. It we be developed in consultation with Ops and M. Tapley. When Ralph is tested to emit interference, it will run at its fastest clock rate acquiring in either TDI Color or TDI Pan. These have the highest clock rates and largest voltage swings, and are expected to produce the most interference. When Ralph is tested to receive interference, it will run at its fastest clock rate acquiring in either LEISA RAW or TDI Pan. The first is expected to be more susceptible under most conditions; the latter may be more sensitive depending on the source of the interference. We monitor the Ralph Status ApID 500 continually; data volume at 65 bps is negligible (< 2 Mbit/hr)

## 009 Stray
COMMISSIONING SKELETON SCIENCE ACTIVITY PLAN REQUIREMENT FORM |  | High-Speed Data Volume
Data Item | Entry | Mode | Mbits/frame | Frames | Fraction | Tot Mbits
Date Updated |  | Framing | 8 | 0 | 1 | 0
Commissioning Requirement Number | Ralph-009 | Pan 1 | 0.06 | 0 | 1 | 0
Commissioning Requirement Name | Stray Light Test | Pan 2 | 0.06 | 0 | 1 | 0
Objective | Use LEISA and MVIC to map Ralph's stray light pattern at 25-50 deg at two roll angles. | Pan Bin | 0.04 | 0 | 1 | 0
Estimated Max Power (Watts) | 6.11 W (MVIC Color Mode) | MVIC Color | 0.24 | 17360 | 0.01 | 41.664
Estimated Total Data (Mbits) | 105.664 | LEISA CDS | 0.8 | 160 | 0.5 | 64
Estimated Time to Complete | 1 hour | LEISA RAW | 1.6 | 0 | 1 | 0
Real Time Contact Requirement | No | Total |  |  |  | 105.664
Pointing Requirement | 3-axis. Two arbitrary boresight roll angles, separated by 90 deg (see below). Ralph can safely point directly at Sun. LORRI can safely point 10 deg from Sun. This phase gets no closer than 25 deg from Sun.
Other Instrument Required | None
Special S/C Requirements | None
STOL (R/T) SEQ or Stored Command SEQ | Stored Command SEQ
Timing Constraints | Prefer beyond 4 AU to reduce magnitude of stray light signal. 3.5 AU is acceptable.
Precursor Commissioning Requirements | Ralph-004
Brief Synopsis and Notes:
We here measure stray light from the Sun at two roll angles at 25-50 deg. In a different commissioning phase, we go to smaller angles using a fainter source, such as Jupiter. Using the Sun as a source, LEISA saturates inward of ~30 deg, and MVIC will saturate inward of ~40 deg, based on BATC and HBT estimates. We will scan from 50-25 deg, then do a 90 deg roll, and repeat the scan along the same path but in the opposite direction (25-50 deg). This will allows us to get data in both the cross-scan and in-scan directions. These two curves are predicted to be similar but will neither will have been measured on the ground. On the second slew, MVIC and LEISA will be operated such that the TDI direction is normal to the scan direction. This would normally cause smear, but is OK here because stray light is a very extended source. 40-50 deg: MVIC COLOR, highest scan rate, observing continually but downlinking only 1% windowed portion of data (e.g., 50 columns of MVIC's 5000, in each color). A small portion may be downlinked at full resolution to identify any stray light pattern features. 25-40 deg: LEISA, highest scan rate, observing for 1 sec every minute (to reduce data volume). 5-25 deg: Jupiter target, combined with CB3 test. Part of Jupiter sequencing, not commissioning. We monitor the Ralph Status ApID 500 continually; data volume at 65 bps is negligible (< 2 Mbit)

## 009
Ralph-009 Commanding -- Stray Light Test H. Throop
Step | Action | Comment | Time(s) | Total Time (s)
1 | RALPH_DEC_HTR_POWER OFF | Turn off Ralph decontamination heaters 10 hours before start of sequence | 1
2 | POSITION BORESIGHT TO 50 DEG FROM SUN, MVIC DIRECTION NORMAL TO SUN-SPACECRAFT LINE |  | 3600 | 3600
3 | TIGHTEN DEADBAND TO 1 DEG (POSITION) AND 35 URAD/S (RATE) INHIBIT THRUSTERS | Loose deadband -- extended source |  | 3600
3 | RALPH_LVPS_POWER A_CDBOTH ON | Spacecraft powers Ralph. | 14 | 3614 | Orange - G&C command
4 | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph, and wait 1 second | 2 | 3616 | Yellow - Spacecraft command
5 | CMD RALPH_GROUP_RLY MVIC_TDI_COLOR | Set up relays for TDI COLOR | 1 | 3617 | White - Ralph command
6 | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off the relay bus, and wait 1 second | 2 | 3619 | All slew times are taken as 150 sec min (TBR).
7 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 3629
8 | INITIATE SCAN FROM 50 DEG TO 35 DEG: 450 URAD/SEC. SCAN WILL TAKE 140 SEC. OBSERVE WITH MVIC CONTINUALLY, INHIBIT THRUSTERS. | 450 urad/sec = 7.3 Hz |  | 3629
9 | CMD_RALPH_MVIC COLOR | Acquire data using calculated TMR rate | 140 | 3769
10 | CMD_RALPH_IDLE |  | 5 | 3774
11 | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph, and wait 1 second | 2 | 3776
12 | CMD RALPH_GROUP_RLY ALL_OFF | Set up relays for LEISA | 1 | 3777
13 | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off the relay bus, and wait 1 second | 2 | 3779
14 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 3789
15 | CONTINUE SCAN FROM 35 DEG TO 25 DEG: 1240 URAD/SEC. SCAN WILL TAKE 660 SEC. OBSERVE WITH LEISA FOR 1 SEC EVERY MIN AT HIGHEST RATE. INHIBIT THRUSTERS. | 1240 URAD/SEC = 62 Hz |  | 3789
16 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 3790
17 | CMD_RALPH_IDLE |  | 59 | 3849
18 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 3850
19 | CMD_RALPH_IDLE |  | 59 | 3909
20 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 3910
21 | CMD_RALPH_IDLE |  | 59 | 3969
22 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 3970
23 | CMD_RALPH_IDLE |  | 59 | 4029
24 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 4030
25 | CMD_RALPH_IDLE |  | 59 | 4089
26 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 4090
27 | CMD_RALPH_IDLE |  | 59 | 4149
28 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 4150
29 | CMD_RALPH_IDLE |  | 59 | 4209
30 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 4210
31 | CMD_RALPH_IDLE |  | 59 | 4269
32 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 4270
33 | CMD_RALPH_IDLE |  | 59 | 4329
34 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 4330
35 | CMD_RALPH_IDLE |  | 59 | 4389
36 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 4390
37 | CMD_RALPH_IDLE |  | 59 | 4449
38 | REPOSITION BY ROLLING BORESIGHT 90 DEG (EITHER DIRECTION) FROM PREVIOUS ORIENTATION. NO POSITION CHANGE. |  | 240 | 4689
39 | PERFORM SCAN IN REVERSE DIRECTION FROM 25 DEG TO 35 DEG: 1240 URAD/SEC. SCAN WILL TAKE 660 SEC. OBSERVE WITH LEISA FOR 1 SEC EVERY MIN AT HIGHEST RATE. THRUSTERS INHIBITED. | 1240 URAD/SEC = 62 Hz |  | 4689
40 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 4690
41 | CMD_RALPH_IDLE |  | 59 | 4749
42 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 4750
43 | CMD_RALPH_IDLE |  | 59 | 4809
44 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 4810
45 | CMD_RALPH_IDLE |  | 59 | 4869
46 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 4870
47 | CMD_RALPH_IDLE |  | 59 | 4929
48 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 4930
49 | CMD_RALPH_IDLE |  | 59 | 4989
50 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 4990
51 | CMD_RALPH_IDLE |  | 59 | 5049
52 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 5050
53 | CMD_RALPH_IDLE |  | 59 | 5109
54 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 5110
55 | CMD_RALPH_IDLE |  | 59 | 5169
56 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 5170
57 | CMD_RALPH_IDLE |  | 59 | 5229
58 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 5230
59 | CMD_RALPH_IDLE |  | 59 | 5289
60 | CMD_RALPH_LEISA 125 | Acquire LEISA data | 1 | 5290
61 | CMD_RALPH_IDLE |  | 59 | 5349
62 | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph, and wait 1 second | 2 | 5351
63 | CMD RALPH_GROUP_RLY MVIC_TDI_COLOR | Set up MVIC for TDI color. | 1 | 5352
64 | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off the relay bus, and wait 1 second | 2 | 5354
65 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 5364
66 | CONTINUE SCAN FROM 35 DEG TO 50 DEG : 450 URAD/SEC. SCAN WILL TAKE 140 SECONDS. OBSERVE WITH MVIC CONTINUALLY. THRUSTERS INHIBITED. | 450 urad/sec = 7.3 Hz |  | 5364
67 | CMD_RALPH_MVIC COLOR | Acquire data using calculated TMR rate | 140 | 5504
68 | CMD_RALPH_IDLE |  | 5 | 5509
69 | RALPH_LVPS_POWERA_CDBOTH OFF | S/C turns off Ralph | 1 | 5510
70 | RALPH_DEC_HTR_POWER ON | Turn on decontamination heaters | 1 | 5511

## 010 SIA
COMMISSIONING SKELETON SCIENCE ACTIVITY PLAN REQUIREMENT FORM |  | High-Speed Data Volume
Data Item | Entry | Mode | Mbits/frame | Frames | Fraction | Tot Mbits
Date Updated |  | Framing | 8 | 0 | 1 | 0
Commissioning Requirement Number | Ralph-010 | Pan 1 | 0.06 | 0 | 1 | 0
Commissioning Requirement Name | Solar Illumination Aperture (SIA) Test | Pan 2 | 0.06 | 0 | 1 | 0
Objective | Perform a single 4.5 deg scan through both the 40x and non-attenuated entrances to the Ralph SIA. | Pan Bin | 0.04 | 0 | 1 | 0
Estimated Max Power (Watts) | 6.11 W (MVIC Color Mode) | MVIC Color | 0.24 | 3900 | 0.05 | 46.8
Estimated Total Data (Mbits) | 46.8 | LEISA CDS | 0.8 | 0 | 1 | 0
Estimated Time to Complete | 1 hour | LEISA RAW | 1.6 | 0 | 1 | 0
Real Time Contact Requirement | No | Total |  |  |  | 46.8
Pointing Requirement | SIA toward Sun (3-axis; arbitrary roll angle). Because SIA is mounted at 90 deg to prime Ralph entrance, this observation will not affect other bore-sighted instruments (e.g., LORRI0.
Other Instrument Required | None
Special S/C Requirements | None
STOL (R/T) SEQ or Stored Command SEQ | Stored Command SEQ
Timing Constraints | None
Precursor Commissioning Requirements | Ralph-004
Brief Synopsis and Notes:
We will perform a single scan to map out the 1-D behavior of both the 40x and non-attenuated SIA apertures. We will scan at the highest rate possible, using the TDI NIR channel, which is furthest from the FOV center and therefore most likely to show any gross anomalies. The two aperture centers are separated by ~1.6 deg, and each has a width of ~0.5 deg. The scan length of 4.6 deg will cover both apertures with a 1 deg pad beyond the FOV on each side. Data will be windowed before downlink (e.g., 250 of Ralph's lines), with a high-resolution portion downlinked as necessary. We monitor the Ralph Status ApID 500 continually; data volume at 65 bps is negligible (< 2 Mbit)

## 010
Ralph-010 Commanding -- SIA Test H. Throop
Step | Action | Comment | Time(s) | Total Time (s)
1 | RALPH_DEC_HTR_POWER OFF | Turn off Ralph decontamination heaters 10 hours before start of sequence | 1
2 | POSITION RALPH WITH SUN 1.5 DEG AWAY FROM 40x-ATTENUATED SIA CENTER, ALONG LINE CONNECTING TWO SIA APERTURES. TIGHTEN DEADBAND TO SMALLEST NOMINAL RATE AND POSITION. |  | 3600 | 3600
3 | RALPH_LVPS_POWER A_CDBOTH ON | Spacecraft powers Ralph. | 14 | 3614 | Orange - G&C command
4 | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph, and wait 1 second | 2 | 3616 | Yellow - Spacecraft command
5 | CMD RALPH_GROUP_RLY MVIC_TDI_COLOR | Set up relays for TDI COLOR | 1 | 3617 | White - Ralph command
6 | RALPH_RELAY_POWER A_CDBOTH OFF | Turn off the relay bus, and wait 1 second | 2 | 3619 | All slew times are taken as 150 sec min (TBR).
7 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enable the recorder. | 10 | 3629
8 | INITIATE SCAN TOWARD 40x AND 1x SIA APERTURES: 1040 URAD/SEC, 4.6 DEG=3900 FRAMES. CROSS-TRACK STABILIZED; THRUSTERS ARE NOT INHIBITED. | 1040 urad/sec = 52 Hz |  | 3629
9 | CMD_RALPH_MVIC_COLOR | Acquire data using calculated TMR rate | 75 | 3704
10 | CMD_RALPH_IDLE |  | 1 | 3705
11 | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph, and wait 1 second | 2 | 3707
12 | CMD_RALPH_GROUP_RLY ALL_OFF | Turn off all the relays | 1 | 3708
13 | RALPH_RELAY_POWERA_CDBOTH_OFF | Turn off the relay bus, and wait 1 second | 2 | 3710
14 | RALPH_LVPS_POWERA_CDBOTH OFF | S/C turns off Ralph | 1 | 3711
15 | RALPH_DEC_HTR_POWER ON | Turn on decontamination heaters | 1 | 3712

## 011 OpNav End-to-End
COMMISSIONING SKELETON SCIENCE ACTIVITY PLAN REQUIREMENT FORM |  | High-Speed Data Volume
Data Item | Entry | Mode | Mbits/frame | Frames | Fraction | Tot Mbits
Date Updated |  | Framing | 8 | 6 | 1 | 48
Commissioning Requirement Number | Ralph-011 | Pan 1 | 0.06 | 0 | 1 | 0
Commissioning Requirement Name | OpNav Test | Pan 2 | 0.06 | 0 | 1 | 0
Objective | Perform end-to-end Optical Navigation test | Pan Bin | 0.04 | 0 | 1 | 0
Estimated Max Power (Watts) | ? | MVIC Color | 0.24 | 0 | 1 | 0
Estimate Total Data (Mbits) | 48 | LEISA CDS | 0.8 | 0 | 1 | 0
Estimated Time to Complete | 30 min per 6 image set | LEISA RAW | 1.6 | 0 | 1 | 0
Real Time Contact Requirement | no | Total |  |  |  | 48
Pointing Requirement | targets tbd
Other Instrument Required | None
Special S/C Requirements | None
STOL (R/T) SEQ or Stored Command SEQ | SEQ
Timing Constraints | After Ralph-010
Precursor Commissioning Requirements | Ralph-004
Brief Synopsis and Notes:
We would like to do an end-to-end test of the OpNav process. This will involve using aqcuisitions with the RALPH_MVIC_PAN_FRAME mode and ground-based processing. Details of implementation are up to s/c operations and navigation teams. These are end-to-end tests to practice several of the critical Pluto or Charon OpNav acquisitions using Uranus or Neptune or a dark satellite of Jupiter. Acquire images of a dark object when it is a comparable brightness (if possible) to what Pluto will be during the acquisition of the Pluto OpNav sets. Possible data sets to emulate are the OpNavs at P-510d, -365d, -300d, -403d, -95d, -50d, -20d, -7d, -2d, -12hr. For some of these Pluto is resolved, for some Pluto is sub-pixel. Ideally, we would want to test both cases, but it is not possible to find a target dim enough to not saturate if resolved. 1) Resolved target: There are no resolved, unsaturated targets that we know of. Jupiter and its moons are too bright, and Uranus/Neptune are both sub-pixel from Jupiter. We can still do the resolved case if Bobby thinks there is any merit despite the saturation problem. 2) Sub-pixel target: TBD. It is desired to do 3 tests during the Commissioning period. For each test, take 6 images of a dark Jovian satellite or other dark target (Uranus or Neptune?) timed so that the stars and target do not light up the same pixels. Use motion of the deadband to provide offset. Distance to the object can be scaled to emulate the brightness of the actual Pluto image. Repeat the 6 images approximately 1 week later or whenever a change in the position of the target relative to the spacecraft of 10 pixels can be detected. Each test consists therefore of 12 images. Need to select the 3 opportunities. Data volume would be 3 tests x 92 Mb per test (12 frames each) = 276 Mb We monitor the Ralph Status ApID 500 continually; data volume at 65 bps is negligible (< 2 Mbit)

## 011
Ralph-011 Commanding: OpNav End-to-End A. Harch
Step | Action | Comment | Time(s) | Total Time (s) | Legend
1 | RALPH_DEC_HTR_POWER OFF | Turn off Ralph decontamination heaters 10 hours before start of sequence | 1
2 | POINT S/C TO TARGET TIGHTEN DEADBANDS TO SMALLEST NOMINAL RATE AND POSITION. |  | 3600 | 3600
3 | RALPH_LVPS_POWER A_CDBOTH ON | Spacecraft powers Ralph. | 14 | 3614 | Orange - G&C command
4 | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph (SC command), and wait 1 second | 2 | 3616 | Yellow - Spacecraft command
5 | CMD RALPH_SIDESEL_RLY | Pull relays to correct DE side, and wait | 1 | 3617 | White - Ralph command
6 | CMD RALPH_GROUP_RLY MVIC_PAN_FRAME | Turn on relays for mvic pan frame mode | 1 | 3618 | All slew times are taken as 150 sec min (TBR).
7 | RALPH_RELAY_POWERA_CDBOTH_OFF | Turn off the relay bus (SC command), and wait 1 second | 2 | 3620
8 | SSR SETUP COMMANDS | Set up the SSR with the high speed mode and enabling the recorder. | 10 | 3610
9 | INHIBIT THRUSTERS |  |  | 0
9 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 1 (short) | 10 | 3620
10 | CMD_RALPH_IDLE |  | 1 | 3621
11 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 1 (short) | 10 | 3631
12 | CMD_RALPH_IDLE |  | 1 | 3632
13 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 2 (med) | 10 | 3642
14 | CMD_RALPH_IDLE |  | 1 | 3643
15 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 2 (med) | 10 | 3653
16 | CMD_RALPH_IDLE |  | 1 | 3654
17 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 3 (long) | 10 | 3664
18 | CMD_RALPH_IDLE |  | 1 | 3665
19 | CMD_RALPH_MVIC PAN_FRAME TBD | Acquire 1 frame exp 3 (long) | 10 | 3675
20 | CMD_RALPH_IDLE |  | 1 | 3676
21 | RALPH_RELAY_POWER A_CDBOTH ON | Energize the relay bus for Ralph (SC command), and wait 1 second | 2 | 3678
22 | CMD_RALPH_GROUP_RLY ALL_OFF | Turn off all the relays | 1 | 3679
23 | RALPH_RELAY_POWERA_CDBOTH_OFF | Turn off the relay bus (SC command), and wait 1 second | 2 | 3681
24 | RALPH_LVPS_POWERA_CDBOTH OFF | S/C turns off Ralph | 1 | 3682
25 | RALPH_DEC_HTR_POWER ON | Turn on decontamination heaters | 1 | 3683
*timing of frames tbd, need to look at expected deadband performance
Repeat a week later?

## 012 EEPROM Maintenence
COMMISSIONING SKELETON SCIENCE ACTIVITY PLAN REQUIREMENT FORM |  | High-Speed Data Volume
Data Item | Entry | Mode | Mbits/frame | Frames | Fraction | Tot Mbits
Date Updated |  | Framing | 8 | 0 | 1 | 0
Commissioning Requirement Number | Ralph-012 | Pan 1 | 0.06 | 0 | 1 | 0
Commissioning Requirement Name | EEPROM Maintenance | Pan 2 | 0.06 | 0 | 1 | 0
Objective | Perform maintenance activities for EEPROM, before s/c hibernation | Pan Bin | 0.04 | 0 | 1 | 0
Estimated Max Power (Watts) | 4.5 W (no science data acquisition) | MVIC Color | 0.24 | 0 | 1 | 0
Estimate Total Data (Mbits) | Low-speed telemetry only. EEPROM images to be downloaded are 40K each (minimal) | LEISA CDS | 0.8 | 0 | 1 | 0
Estimated Time to Complete | 2 8-hour passes | LEISA RAW | 1.6 | 0 | 1 | 0
Real Time Contact Requirement | Yes, since verification is desired after EEPROM refresh or reprogramming | Total |  |  |  | 0
Pointing Requirement | None
Other Instrument Required | None
Special S/C Requirements | None
STOL (R/T) SEQ or Stored Command SEQ | Either, depending on s/c command block space (see below)
Timing Constraints | Before post-Jupiter hibernation.
Precursor Commissioning Requirements | All other phases inclusive.
Brief Synopsis and Notes:
Purpose of the segment is to refresh the EEPROM code. Even if the bits returned are correct, regular re-programming can improve EEPROM reliability in the future. We may also use this segment to update firmware version as needed. Presumably a sequence similar to this may be performed during the annual checkouts, but this is outside the realm of commissioning. A total of six copies of the Ralph firmware are stored onboard the instrument: three blocks each (for triple-voting) on sides A and B. The code is ~40K long, stored in five 8K segments. (Each 8K segment corresponds to one line in Eddie's spreadsheet). These 8K segments are uploaded in 128-byte chunks to the instrument. Each 40K block also has an associated EEPROM table space. Right now the upload goes through the 'scratch' area (onboard the s/c). This may or may not be necessary, based on the s/c command block space. Alice will look into this. This also plays relevance to whether we use STOL or sequenced commanding, and what macro capability is available. (Other than this, no reason to do STOL, although we do want to have real-time downlink in order to confirm proper programming before continuing.)
1. Calculate and downlink the current checksum for all three Blocks (side A) 2. Downlink current images for all three Blocks 3. Upload Block 1 4. Calculate Block 1 checksum and downlink 5. Proceed only after ground has confirmed proper EEPROM programming using checksum 6. Upload Blocks 2, 3 and Tables 7. Downlink checksums for Blocks 2, 3, and Tables but do not wait for ground confirmation after each. 8. Power-cycle instrument on side A and confirm proper startup. 9. Repeat 1-8 for side B. We monitor the Ralph Status ApID 500 continually; data volume at 65 bps is negligible (< 2 Mbit/hour)

## 012
Ralph-012 Commanding -- EEPROM Maintenance E. Weigle
Step |  | Action | Comment | Time(s) | Total Time (s) | Low Speed output (bytes/sec) | Hi Speed output (bytes/sec)
1 |  | RALPH_DEC_HTR_POWER OFF | Turn off Ralph decontamination heaters 10 hours before start of sequence | 1
2 |  | RALPH_LVPS_POWER A_CDBOTH ON | Spacecraft powers Ralph. | 14 | 14 | 0 | 0 | Blue - Comments
3 |  | CMD RALPH_STATE CHECKOUT | Put Ralph in Checkout State | 2 | 16 | 69 | 0 | Yellow - Spacecraft command
4 | checksum code 3 | CMD RALPH_LOAD_MEMORY 0 0x9FFB NORMAL CHKSUM EEPCODE1 $EXP_CHKSUM 0 0 0 … 0 | Checksum the images first, so we have some sort of indication if the EEPROM is degrading. | 15 | 31 | 69 | 0 | Green - Pause here until we decide it is okay to proceed. This implies waiting before executing the current line
5 | checksum code 1 | CMD RALPH_LOAD_MEMORY 0 0x9FFB NORMAL CHKSUM EEPCODE2 $EXP_CHKSUM 0 0 0 … 0 | Checksum the images first, so we have some sort of indication if the EEPROM is degrading. | 15 | 46 | 69 | 0 | Purple - Commands dealing with binary EEPROM images.
6 | checksum code 2 | CMD RALPH_LOAD_MEMORY 0 0x9FFB NORMAL CHKSUM EEPCODE3 $EXP_CHKSUM 0 0 0 … 0 | Checksum the images first, so we have some sort of indication if the EEPROM is degrading. | 15 | 61 | 69 | 0 | White - Ralph command
7 | Checksum table 1 | CMD RALPH_LOAD_MEMORY 0 0x800 NORMAL CHKSUM EEPTABLE1 $EXP_CHKSUM 0 0 0 … 0 | Now checksum the entire table space (all 3 tables) to verify that other data space remained intact. | 15 | 76 | 69 | 0
8 | Checksum table 2 | CMD RALPH_LOAD_MEMORY 0 0x800 NORMAL CHKSUM EEPTABLE2 $EXP_CHKSUM 0 0 0 … 0 | Now checksum the entire table space (all 3 tables) to verify that other data space remained intact. | 15 | 91 | 69 | 0
9 | Checksum table 3 | CMD RALPH_LOAD_MEMORY 0 0x800 NORMAL CHKSUM EEPTABLE3 $EXP_CHKSUM 0 0 0 … 0 | Now checksum the entire table space (all 3 tables) to verify that other data space remained intact. | 15 | 106 | 69 | 0
| Dump image 1 | CMD RALPH_DUMP_MEMORY 0 0xA000 NORMAL DUMP EEPCODE1 | Dump code image 1. The dump times assume the SC has the memory dump bit set to okay, which allows us to immediately begin dumping. If not, then subsequent dumps will likely be rejected, because the previous dump will not be completed. | 70 |  | 69 | 0
| Dump image 2 | CMD RALPH_DUMP_MEMORY 0 0xA000 NORMAL DUMP EEPCODE2 | Dump code image 2 | 70 |  | 219 | 0
| Dump image 3 | CMD RALPH_DUMP_MEMORY 0 0xA000 NORMAL DUMP EEPCODE3 | Dump code image 3 | 70 |  | 219 | 0
| Dump table 1 | CMD RALPH_DUMP_MEMORY 0 0xA000 NORMAL DUMP EEPTABLE1 | Dump table 1 | 20 |  | 219 | 0
| Dump table 2 | CMD RALPH_DUMP_MEMORY 0 0xA000 NORMAL DUMP EEPTABLE2 | Dump table 2 | 20 |  | 219 | 0
| Dump table 3 | CMD RALPH_DUMP_MEMORY 0 0xA000 NORMAL DUMP EEPTABLE3 | Dump table 3 | 20 |  | 219 | 0
10 | Load to EEPROM code image 1 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg1.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 1 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 176 | 69 | 0
11 |  | CMD RALPH_LOAD_MEMORY 0x00 NORMAL PATCH EEPCODE1 "code_seg1.bin" | Patch to EEPROM CODE image 1 space | 15 | 191 | 69 | 0
12 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg2.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 2 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 261 | 69 | 0
13 |  | CMD RALPH_LOAD_MEMORY 0x2000 NORMAL PATCH EEPCODE1 "code_seg2.bin" | Patch to EEPROM CODE image 1 space | 15 | 276 | 69 | 0
14 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg3.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 3 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 346 | 69 | 0
15 |  | CMD RALPH_LOAD_MEMORY 0x4000 NORMAL PATCH EEPCODE1 "code_seg3.bin" | Patch to EEPROM CODE image 1 space | 15 | 361 | 69 | 0
16 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg4.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 4 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 431 | 69 | 0
17 |  | CMD RALPH_LOAD_MEMORY 0x6000 NORMAL PATCH EEPCODE1 "code_seg4.bin" | Patch to EEPROM CODE image 1 space | 15 | 446 | 69 | 0
18 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg5.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 5 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 516 | 69 | 0
19 |  | CMD RALPH_LOAD_MEMORY 0x8000 NORMAL PATCH EEPCODE1 "code_seg5.bin" | Patch to EEPROM CODE image 1 space | 15 | 531 | 69 | 0
20 | checksum code 1 | CMD RALPH_LOAD_MEMORY 0 0x9FFB NORMAL CHKSUM EEPCODE1 $EXP_CHKSUM 0 0 0 … 0 | individual segment checksums were verified in the upload process, but we will check the byte-wide XOR checksum of the entire image (minus the last double-word, that is where the double word checksum for triple-voting is located) This way we know the other parts of the EEPCODE1 weren't corrupted loading the rest of the image. | 15 | 546 | 69 | 0
|  | Wait for response (TBR: We can Pause only in STOL, not SEQ) | Determine if EEPROM 1 loaded okay by verfiying the checksum. If it is okay, then proceed, if not, then determine if the best course is to continue loading images. |  |  | 69
21 | load code 2 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg1.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 1 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 616 | 69 | 0
22 |  | CMD RALPH_LOAD_MEMORY 0x00 NORMAL PATCH EEPCODE2 "code_seg1.bin" | Patch to EEPROM CODE image 2 space | 15 | 631 | 69 | 0
23 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg2.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 2 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 701 | 69 | 0
24 |  | CMD RALPH_LOAD_MEMORY 0x2000 NORMAL PATCH EEPCODE2 "code_seg2.bin" | Patch to EEPROM CODE image 2 space | 15 | 716 | 69 | 0
25 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg3.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 3 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 786 | 69 | 0
26 |  | CMD RALPH_LOAD_MEMORY 0x4000 NORMAL PATCH EEPCODE2 "code_seg3.bin" | Patch to EEPROM CODE image 2 space | 15 | 801 | 69 | 0
27 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg4.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 4 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 871 | 69 | 0
28 |  | CMD RALPH_LOAD_MEMORY 0x6000 NORMAL PATCH EEPCODE2 "code_seg4.bin" | Patch to EEPROM CODE image 2 space | 15 | 886 | 69 | 0
29 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg5.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 5 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 956 | 69 | 0
30 |  | CMD RALPH_LOAD_MEMORY 0x8000 NORMAL PATCH EEPCODE2 "code_seg5.bin" | Patch to EEPROM CODE image 2 space | 15 | 971 | 69 | 0
31 | checksum code 2 | CMD RALPH_LOAD_MEMORY 0 0x9FFB NORMAL CHKSUM EEPCODE2 $EXP_CHKSUM 0 0 0 … 0 | individual segment checksums were verified in the upload process, but we will check the byte-wide XOR checksum of the entire image (minus the last double-word, that is where the double word checksum for triple-voting is located) This way we know the other parts of the EEPCODE1 weren't corrupted loading the rest of the image. | 15 | 986 | 69 | 0
32 | load code 3 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg1.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 1 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 1056 | 69 | 0
33 |  | CMD RALPH_LOAD_MEMORY 0x00 NORMAL PATCH EEPCODE3 "code_seg1.bin" | Patch to EEPROM CODE image 3 space | 15 | 1071 | 69 | 0
34 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg2.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 2 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 1141 | 69 | 0
35 |  | CMD RALPH_LOAD_MEMORY 0x2000 NORMAL PATCH EEPCODE3 "code_seg2.bin" | Patch to EEPROM CODE image 3 space | 15 | 1156 | 69 | 0
36 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg3.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 3 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 1226 | 69 | 0
37 |  | CMD RALPH_LOAD_MEMORY 0x4000 NORMAL PATCH EEPCODE3 "code_seg3.bin" | Patch to EEPROM CODE image 3 space | 15 | 1241 | 69 | 0
38 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg4.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 4 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 1311 | 69 | 0
39 |  | CMD RALPH_LOAD_MEMORY 0x6000 NORMAL PATCH EEPCODE3 "code_seg4.bin" | Patch to EEPROM CODE image 3 space | 15 | 1326 | 69 | 0
40 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg5.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 5 of 5. Real STOL has a feature to upload an entire file,however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 1396 | 69 | 0
41 |  | CMD RALPH_LOAD_MEMORY 0x8000 NORMAL PATCH EEPCODE3 "code_seg5.bin" | Patch to EEPROM CODE image 3 space | 15 | 1411 | 69 | 0
42 | checksum code 3 | CMD RALPH_LOAD_MEMORY 0 0x9FFB NORMAL CHKSUM EEPCODE3 $EXP_CHKSUM 0 0 0 … 0 | individual segment checksums were verified in the upload process, but we will check the byte-wide XOR checksum of the entire image (minus the last double-word, that is where the double word checksum for triple-voting is located) This way we know the other parts of the EEPCODE1 weren't corrupted loading the rest of the image. | 15 | 1426 | 69 | 0
43 | checksum code 1 | CMD RALPH_LOAD_MEMORY 0 0x9FFB NORMAL CHKSUM EEPCODE1 $EXP_CHKSUM 0 0 0 … 0 | Now check EEPCODE1 image again, since all three images reside on the same device, we want to be sure that nothing was corrupted during other loading. | 15 | 1441 | 69 | 0
44 | checksum code 2 | CMD RALPH_LOAD_MEMORY 0 0x9FFB NORMAL CHKSUM EEPCODE2 $EXP_CHKSUM 0 0 0 … 0 | Now check EEPCODE2 image again, since all three images reside on the same device, we want to be sure that nothing was corrupted during other loading. | 15 | 1456 | 69 | 0
45 | Load Table 1 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "tables.bin" | Send the command to upload a file to the SCRATCH area. This is the table data image. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. | 25 | 1481 | 69 | 0
46 |  | CMD RALPH_LOAD_MEMORY 0x8000 NORMAL PATCH EEPTABLE1 "tables.bin" | Patch to EEPROM TABLE 1 space | 7 | 1488 | 69 | 0
47 | Load table 2 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "tables.bin" | Send the command to upload a file to the SCRATCH area. This is the table data image. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. | 25 | 1513 | 69 | 0
48 |  | CMD RALPH_LOAD_MEMORY 0x8000 NORMAL PATCH EEPTABLE2 "tables.bin" | Patch to EEPROM TABLE 2 space | 7 | 1520 | 69 | 0
49 | Load Table 3 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "tables.bin" | Send the command to upload a file to the SCRATCH area. This is the table data image. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. | 25 | 1545 | 69 | 0
50 |  | CMD RALPH_LOAD_MEMORY 0x8000 NORMAL PATCH EEPTABLE3 "tables.bin" | Patch to EEPROM TABLE 3 space | 7 | 1552 | 69 | 0
51 | Checksum table space | CMD RALPH_LOAD_MEMORY 0 0x800 NORMAL CHKSUM EEPTABLE1 $EXP_CHKSUM 0 0 0 … 0 | checksum table 1 | 15 | 1567 | 69 | 0
52 | Checksum table space | CMD RALPH_LOAD_MEMORY 0 0x800 NORMAL CHKSUM EEPTABLE2 $EXP_CHKSUM 0 0 0 … 0 | checksum table 2 | 15 | 1582
53 | Checksum table space | CMD RALPH_LOAD_MEMORY 0 0x800 NORMAL CHKSUM EEPTABLE3 $EXP_CHKSUM 0 0 0 … 0 | checksum table 3 | 15 | 1597
54 |  | RALPH_HW_RST_RESET A_CDA | Do a sc hard reset to invoke Ralph to boot from scratch. Sit here for 20 seconds so we can collect telemetery to verify the boot options. | 20 | 1617 | 69 | 0
55 |  | RALPH_LVPS_POWER A_CDBOTH OFF | Turn PRIME side of RALPH Off | 2 | 1619
56 |  | RALPH_LVPS_POWER B_CDBOTH ON | Spacecraft powers Ralph. | 14 | 1633 | 69 | 0
57 |  | CMD RALPH_STATE CHECKOUT | Put Ralph in Checkout State | 2 | 1635 | 69 | 0
58 | checksum code 3 | CMD RALPH_LOAD_MEMORY 0 0x9FFB NORMAL CHKSUM EEPCODE1 $EXP_CHKSUM 0 0 0 … 0 | Checksum the images first, so we have some sort of indication if the EEPROM is degrading. | 15 | 1650 | 69 | 0
59 | checksum code 1 | CMD RALPH_LOAD_MEMORY 0 0x9FFB NORMAL CHKSUM EEPCODE2 $EXP_CHKSUM 0 0 0 … 0 | Checksum the images first, so we have some sort of indication if the EEPROM is degrading. | 15 | 1665 | 69 | 0
60 | checksum code 2 | CMD RALPH_LOAD_MEMORY 0 0x9FFB NORMAL CHKSUM EEPCODE3 $EXP_CHKSUM 0 0 0 … 0 | Checksum the images first, so we have some sort of indication if the EEPROM is degrading. | 15 | 1680 | 69 | 0
61 | Checksum table 1 | CMD RALPH_LOAD_MEMORY 0 0x800 NORMAL CHKSUM EEPTABLE1 $EXP_CHKSUM 0 0 0 … 0 | Now checksum the entire table space (all 3 tables) to verify that other data space remained intact. | 15 | 1695 | 69 | 0
62 | Checksum table 2 | CMD RALPH_LOAD_MEMORY 0 0x800 NORMAL CHKSUM EEPTABLE2 $EXP_CHKSUM 0 0 0 … 0 | Now checksum the entire table space (all 3 tables) to verify that other data space remained intact. | 15 | 1710 | 69 | 0
63 | Checksum table 3 | CMD RALPH_LOAD_MEMORY 0 0x800 NORMAL CHKSUM EEPTABLE3 $EXP_CHKSUM 0 0 0 … 0 | Now checksum the entire table space (all 3 tables) to verify that other data space remained intact. | 15 | 1725 | 69 | 0
64 | Dump image 1 | CMD RALPH_DUMP_MEMORY 0 0xA000 NORMAL DUMP EEPCODE1 | Dump code image 1. The dump times assume the SC has the memory dump bit set to okay, which allows us to immediately begin dumping. If not, then subsequent dumps will likely be rejected, because the previous dump will not be completed. | 70 | 1795 | 69 | 0
65 | Dump image 2 | CMD RALPH_DUMP_MEMORY 0 0xA000 NORMAL DUMP EEPCODE2 | Dump code image 2 | 70 | 1865 | 219 | 0
66 | Dump image 3 | CMD RALPH_DUMP_MEMORY 0 0xA000 NORMAL DUMP EEPCODE3 | Dump code image 3 | 70 | 1935 | 219 | 0
67 | Dump table 1 | CMD RALPH_DUMP_MEMORY 0 0xA000 NORMAL DUMP EEPTABLE1 | Dump table 1 | 20 | 1955 | 219 | 0
68 | Dump table 2 | CMD RALPH_DUMP_MEMORY 0 0xA000 NORMAL DUMP EEPTABLE2 | Dump table 2 | 20 | 1975 | 219 | 0
69 | Dump table 3 | CMD RALPH_DUMP_MEMORY 0 0xA000 NORMAL DUMP EEPTABLE3 | Dump table 3 | 20 | 1995 | 219 | 0
70 | Load to EEPROM code image 1 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg1.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 1 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 2065 | 69 | 0
71 |  | CMD RALPH_LOAD_MEMORY 0x00 NORMAL PATCH EEPCODE1 "code_seg1.bin" | Patch to EEPROM CODE image 1 space | 15 | 2080 | 69 | 0
72 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg2.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 2 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 2150 | 69 | 0
73 |  | CMD RALPH_LOAD_MEMORY 0x2000 NORMAL PATCH EEPCODE1 "code_seg2.bin" | Patch to EEPROM CODE image 1 space | 15 | 2165 | 69 | 0
74 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg3.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 3 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 2235 | 69 | 0
75 |  | CMD RALPH_LOAD_MEMORY 0x4000 NORMAL PATCH EEPCODE1 "code_seg3.bin" | Patch to EEPROM CODE image 1 space | 15 | 2250 | 69 | 0
76 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg4.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 4 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 2320 | 69 | 0
77 |  | CMD RALPH_LOAD_MEMORY 0x6000 NORMAL PATCH EEPCODE1 "code_seg4.bin" | Patch to EEPROM CODE image 1 space | 15 | 2335 | 69 | 0
78 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg5.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 5 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 2405 | 69 | 0
79 |  | CMD RALPH_LOAD_MEMORY 0x8000 NORMAL PATCH EEPCODE1 "code_seg5.bin" | Patch to EEPROM CODE image 1 space | 15 | 2420 | 69 | 0
80 | checksum code 1 | CMD RALPH_LOAD_MEMORY 0 0x9FFB NORMAL CHKSUM EEPCODE1 $EXP_CHKSUM 0 0 0 … 0 | individual segment checksums were verified in the upload process, but we will check the byte-wide XOR checksum of the entire image (minus the last double-word, that is where the double word checksum for triple-voting is located) This way we know the other parts of the EEPCODE1 weren't corrupted loading the rest of the image. | 15 | 2435 | 69 | 0
81 |  | Wait for response (TBR: We can Pause only in STOL, not SEQ) | Determine if EEPROM 1 loaded okay by verfiying the checksum. If it is okay, then proceed, if not, then determine if the best course is to continue loading images. |  | 2435 | 69 | 0
82 | load code 2 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg1.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 1 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 2505 | 69 | 0
83 |  | CMD RALPH_LOAD_MEMORY 0x00 NORMAL PATCH EEPCODE2 "code_seg1.bin" | Patch to EEPROM CODE image 2 space | 15 | 2520 | 69 | 0
84 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg2.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 2 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 2590 | 69 | 0
85 |  | CMD RALPH_LOAD_MEMORY 0x2000 NORMAL PATCH EEPCODE2 "code_seg2.bin" | Patch to EEPROM CODE image 2 space | 15 | 2605 | 69 | 0
86 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg3.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 3 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 2675 | 69 | 0
87 |  | CMD RALPH_LOAD_MEMORY 0x4000 NORMAL PATCH EEPCODE2 "code_seg3.bin" | Patch to EEPROM CODE image 2 space | 15 | 2690 | 69 | 0
88 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg4.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 4 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 2760 | 69 | 0
89 |  | CMD RALPH_LOAD_MEMORY 0x6000 NORMAL PATCH EEPCODE2 "code_seg4.bin" | Patch to EEPROM CODE image 2 space | 15 | 2775 | 69 | 0
90 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg5.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 5 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 2845 | 69 | 0
91 |  | CMD RALPH_LOAD_MEMORY 0x8000 NORMAL PATCH EEPCODE2 "code_seg5.bin" | Patch to EEPROM CODE image 2 space | 15 | 2860 | 69 | 0
92 | checksum code 2 | CMD RALPH_LOAD_MEMORY 0 0x9FFB NORMAL CHKSUM EEPCODE2 $EXP_CHKSUM 0 0 0 … 0 | individual segment checksums were verified in the upload process, but we will check the byte-wide XOR checksum of the entire image (minus the last double-word, that is where the double word checksum for triple-voting is located) This way we know the other parts of the EEPCODE1 weren't corrupted loading the rest of the image. | 15 | 2875 | 69 | 0
93 | load code 3 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg1.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 1 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 2945 | 69 | 0
94 |  | CMD RALPH_LOAD_MEMORY 0x00 NORMAL PATCH EEPCODE3 "code_seg1.bin" | Patch to EEPROM CODE image 3 space | 15 | 2960 | 69 | 0
95 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg2.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 2 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 3030 | 69 | 0
96 |  | CMD RALPH_LOAD_MEMORY 0x2000 NORMAL PATCH EEPCODE3 "code_seg2.bin" | Patch to EEPROM CODE image 3 space | 15 | 3045 | 69 | 0
97 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg3.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 3 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 3115 | 69 | 0
98 |  | CMD RALPH_LOAD_MEMORY 0x4000 NORMAL PATCH EEPCODE3 "code_seg3.bin" | Patch to EEPROM CODE image 3 space | 15 | 3130 | 69 | 0
99 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg4.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 4 of 5. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 3200 | 69 | 0
100 |  | CMD RALPH_LOAD_MEMORY 0x6000 NORMAL PATCH EEPCODE3 "code_seg4.bin" | Patch to EEPROM CODE image 3 space | 15 | 3215 | 69 | 0
101 |  | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "code_seg5.bin" | Send the command to upload a file to the SCRATCH area. This code image segment 5 of 5. Real STOL has a feature to upload an entire file,however I'm not sure of the steps to do that. It may be a macro feature. | 70 | 3285 | 69 | 0
102 |  | CMD RALPH_LOAD_MEMORY 0x8000 NORMAL PATCH EEPCODE3 "code_seg5.bin" | Patch to EEPROM CODE image 3 space | 15 | 3300 | 69 | 0
103 | checksum code 3 | CMD RALPH_LOAD_MEMORY 0 0x9FFB NORMAL CHKSUM EEPCODE3 $EXP_CHKSUM 0 0 0 … 0 | individual segment checksums were verified in the upload process, but we will check the byte-wide XOR checksum of the entire image (minus the last double-word, that is where the double word checksum for triple-voting is located) This way we know the other parts of the EEPCODE1 weren't corrupted loading the rest of the image. | 15 | 3315 | 69 | 0
104 | checksum code 1 | CMD RALPH_LOAD_MEMORY 0 0x9FFB NORMAL CHKSUM EEPCODE1 $EXP_CHKSUM 0 0 0 … 0 | Now check EEPCODE1 image again, since all three images reside on the same device, we want to be sure that nothing was corrupted during other loading. | 15 | 3330 | 69 | 0
105 | checksum code 2 | CMD RALPH_LOAD_MEMORY 0 0x9FFB NORMAL CHKSUM EEPCODE2 $EXP_CHKSUM 0 0 0 … 0 | Now check EEPCODE2 image again, since all three images reside on the same device, we want to be sure that nothing was corrupted during other loading. | 15 | 3345 | 69 | 0
106 | Load Table 1 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "tables.bin" | Send the command to upload a file to the SCRATCH area. This is the table data image. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. | 25 | 3370 | 69 | 0
107 |  | CMD RALPH_LOAD_MEMORY 0x8000 NORMAL PATCH EEPTABLE1 "tables.bin" | Patch to EEPROM TABLE 1 space | 7 | 3377 | 69 | 0
108 | Load table 2 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "tables.bin" | Send the command to upload a file to the SCRATCH area. This is the table data image. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. | 25 | 3402 | 69 | 0
109 |  | CMD RALPH_LOAD_MEMORY 0x8000 NORMAL PATCH EEPTABLE2 "tables.bin" | Patch to EEPROM TABLE 2 space | 7 | 3409 | 69 | 0
110 | Load Table 3 | CMD RALPH_LOAD_MEMORY 0 NORMAL SCRATCH SCRATCH "tables.bin" | Send the command to upload a file to the SCRATCH area. This is the table data image. Real STOL has a feature to upload an entire file, however I'm not sure of the steps to do that. | 25 | 3434 | 69 | 0
111 |  | CMD RALPH_LOAD_MEMORY 0x8000 NORMAL PATCH EEPTABLE3 "tables.bin" | Patch to EEPROM TABLE 3 space | 7 | 3441 | 69 | 0
112 | Checksum table space | CMD RALPH_LOAD_MEMORY 0 0x800 NORMAL CHKSUM EEPTABLE1 $EXP_CHKSUM 0 0 0 … 0 | checksum table 1 | 15 | 3456 | 69 | 0
113 | Checksum table space | CMD RALPH_LOAD_MEMORY 0 0x800 NORMAL CHKSUM EEPTABLE2 $EXP_CHKSUM 0 0 0 … 0 | checksum table 2 | 15 | 3471 | 69 | 0
114 | Checksum table space | CMD RALPH_LOAD_MEMORY 0 0x800 NORMAL CHKSUM EEPTABLE3 $EXP_CHKSUM 0 0 0 … 0 | checksum table 3 | 15 | 3486 | 69 | 0
115 |  | RALPH_HW_RST_RESET B_CDA | Do a sc hard reset to invoke Ralph to boot from scratch. Sit here for 20 seconds so we can collect telemetery to verify the boot options. | 20 | 3506 | 69 | 0
116 |  | RALPH_LVPS_POWER B_CDBOTH OFF | Turn PRIME side of RALPH Off | 2 | 3508 | 69 | 0
117 |  | RALPH_DEC_HTR_POWER ON | Turn on decontamination heaters | 1 | 3